## Title Page
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated November 10, 2024 February 11, 2025

## Complete Plan
I. Data Collection and Analysis
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcome | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? | What is the outcome of the task?
A. Collect prospective, admitted, enrollment and non-enrolling student data for analysis and predictive modeling.
B. Develop a series of 5-year enrollment projections and impacts on net tuition revenue
II. Branding, Imaging and Marketing
Action Steps | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? | What is the outcome of the task?
A. Maintain a presence in Baltimore and surrounding regional markets by creating a strategic media plan for print and digital markets.
B. Improve the reputational image of the university to the local community. As a University, we must make a concerted effort to improve our brand, image, and reputation in the local market and community.
C. Maintain a cohesive UBalt look and required standards in graduate and undergraduate recruitment and admission marketing and publication designs.
D. Update admission and graduate program websites.
III. Recruitment
Action Steps | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
A. Develop an admission funnel, beginning with a robust prospective student database.
B. Develop a targeted and strategic communication plan using CRM technology.
C. Increase local and regional constituencies’ campus engagement and partnership efforts.
D. Increase transfer student enrollment.
E. Increase graduate student enrollment.
F. Increase/maintain first-time undergraduate students.
G. Increase active-duty military, veteran, and dependent student enrollment.
H. Increase Latinx Student Enrollment
I. Increase international student enrollment.
J. Faculty Staff Involvement
K. Increase Yield
IV. Affordability
Action Steps | Responsible | Deadline | Resources | Potential Barriers | Objectives | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
A. Strategic Use of Financial Aid for Optimal Enrollment
B. Improve student services and educational programming to include financial literacy.
V. Infrastructure
Action Steps | Responsible | Deadline | Resources | Potential Barriers | Objective | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
A. From Task Force report:
B. Sufficiently staff offices whose primary responsibility is enrollment and enrollment related functions.
C. Improve enrollment processes for efficiency and effectiveness.
D. Create a “Front Door” to The University of Baltimore

## I. DATA COLLECTION ANALYSIS
I. Data Collection and Analysis
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcome | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? | What is the outcome of the task?
A. Collect prospective, admitted, enrollment and non-enrolling student data for analysis and predictive modeling.
1. Establish and hire a data analyst for the EM Division | VP Enrollment Management | Completed | NA | NA | Consistent and reliable data and reports | Data Analyst hired 9/8/21
2. Establish partnerships with internal and external units to develop strategic recruitment publications and communication plans to include advancement (branding campaign, social media, advertising opportunities), alumni (promote outcomes), community colleges etc. | VP Enrollment Management AVP Enrollment Management EM Data Analyst | Complete On-going | NA | General lack of understanding on the use of data for EM | Consistent and reliable data and reports | Updated Dashboards Productivity Reports Funnel Reports Deposit IQ Enrollment Report at Census established Readmit policy changes and counting
3. Establish standard KPIs to measure successes of enrollment | VP Enrollment Management AVP Enrollment Management EM Data Analyst Director of Admission | On-going | NA | None | Standard set of KPIs developed | Year over Year percentages results of key performance indicators: *Increase in Applications *Increase in Admits *Increase in Matriculated (committed to attended) *Increase in Enrolled *Decrease in Melt
4. Gather and share pertinent objective and subjective enrollment data to understand who applies and enrolls into UBalt. | EM Data Analyst AVP Enrollment Management Shaeffer Center | On-going | NA | Competing priorities | Data set is established that is easily accessible and can be updated easily | Live Dashboards Admitted Student Survey Intranet EM Website Implemented
*5 Create communication campaigns that build and sustain interest in UBalt. | Associate Provost Academic Affairs Director of Admission Associate VP Enrollment Management | Completed | TBD | Funding for consultant if needed | Dashboards will be fully functional again and we will have a sustainable model to keep them updated | Completed Spring 2022
6. Build projections model based on enrollment trends, new student enrollment and fall to fall attrition | EM Data Analyst VP Enrollment Management AVP Enrollment Management | Completed with on-going adjustments and fine tuning |  |  |  | Projections model developed, based on new student enrollment and attrition rates, and approved.
7. Build predictive model to determine and target which Students will most likely enroll into UBalt. | EAB VP Enrollment Management AVP Enrollment Management Director of Admission | Completed | TBD | Lack of support for EAB partnership | Predictive model to determine who will most likely enroll | EAB's Deposit IQ delivered and implemented.
8. Design and implement annual admitted and enrolling student surveys with Schaefer Center to understand who and why Students are choosing or not choosing to enroll into UBalt. | VP Enrollment Management EM Data Analyst Schaeffer Center | First survey Fall 22 Surveys administrated each new semester | Funding | Funding issues | Survey will be completed and implemented. Over the next three years, we will be able to look at our trends. | First survey released to fall 22 admitted Students. Spring 23 completed Fall 22 and Spring 23 combined Spring 24 Completed
9. Revise and improve marketing events for all targeted populations. | VP Enrollment Management Institutional Research CFO EM Data Analyst | On-going as actuals are added to the model each Director EM year 5 and 10 year projections completed - 2023 | NA | NA | KPI - % Met or did not meet projections
10. Revise and strengthen UBalt's email campaigns that compliments the written communication flow with call-to-action links, for more effective results. | VP Enrollment Management Provost CFO | Version 2 completed for FY25 projections Version 3 completed | NA | Competing priorities | One projection model, with University goals and projections with Dean input. | Completed for FY23 projections Five year projections with tuition revenue implications completed. Completed a rolled up version of the projections model for FY26
11. Complete competitive market review to provide information to make informed decisions concerning UBalt’s capacity, to verify and/or contradict anecdotal data and stories and test our assumptions against market trends and benchmarks. | Associate Provost EAB AVP EM VP EM | Completed Fall 21 and on-going | TBD | TBD | We will have the environmental scan which will be an important part of the Strategic Enrollment Management Plan | Competitive Market Research - completed for graduate education by EAB. Updated report will be done fall 24 360 Reviews of individual program reviews continue
B. Develop a series of 5-year enrollment projections and impacts on net tuition revenue
1. Assess the demand for new programs and formats to grow enrollment, while also discussing the feasibility of sunsetting programs with historical low enrollment. | Provost Associate Provost Academic Affairs | On-going | EAB Reporting | TBD | Priority program identified by AA | EAB - completed a competitive market scan of all graduate programs Completed MBA, MPA and XXX program reviews
2. Develop realistic sets of enrollment projections to include: | VP Enrollment Management CFO Provost Deans EM Data Analyst | On-going |  | Lack of accurate data |  | Model developed to determine goals and projections based on a set of assumptions. *Year over Year Actuals *Persistence/Attrition Rates *Graduation Actuals
a. Conservative targets based on trend data that are recommended for use with budget projections and net revenue projections. | VP Enrollment Management AVP Enrollment Management CFO EM Data Analyst | On-going |  | Lack of accurate data | Annual goals and projections developed for net revenue and budget projections
b. Realistic projections based on trend data and successful outcomes of strategies. | Provost Deans CFO VP Enrollment Management EM Data Analyst | On-going |  | Lack of accurate data | Enrollment projections developed | Fall 22: meet targets, reduced new student percentage decline by 2% Spring 23: meet targets and year-over-year new student enrollment increased by 5% *Add results

## II BRANDING,IMAGING,MARKETING
II. Branding and Marketing
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? | What is the outcome of the task?
A. Maintain a presence in Baltimore and surrounding regional markets by creating a strategic media plan and digital markets | Senior Director Marketing | On-going | Additional marketing funding | Lack of adequate funding |  | A media plan is dynamic, needing continuous review and updating
1. Create and implement a social media and content marketing strategic plan to expand UBalt’s social engagement’s reach. | Senior Director Marketing Asst Director EM | On-going | Additional marketing funding EM Graduate Assistant | Lack of adequate resources | Admission and EM social media channels established.
2. Establish partnerships with internal and external units to develop strategic recruitment publications and communication plans to include advancement (branding campaign, social media, advertising opportunities), alumni (promote outcomes), community colleges etc. | Senior Director Marketing EAB Asst Director EM Director of Admission | Spring 22 | TBD | TBD |  | Once recruitment materials and strategies partnerships are established, materials and strategies will be implemented annually.
3. Identify key opportunities on campus and within the greater Baltimore community to market and promote UBalt, through community events, fairs, lectures, workshops, tourist areas, airports etc. | Director of Admission Senior Director Marketing Asst Director EM | On-going | TBD | TBD | Attendance in Baltimore area community events | Annual review and update
4 Inform all stakeholders on a regular basis of the marketing plan. | Senior Director Marketing Vice President Advancement | On-going | NA | NA |  | Announcements, semi-annual presentations and updates
5 Create communication campaigns that build and sustain interest in UBalt. | Associate Provost Academic Affairs Director of Admission Associate VP Enrollment Management | On-going | TBD | NA |  | On-going and should be reviewed at least every three years
B. Improve the reputational image of the university to the local community. As a University, we must make a concerted effort to improve our brand, image, and reputation in the local market and community. | Senior Director Marketing Associate VP Enrollment Management Director of Admission Vice President Enrollment Management Faculty/Staff Students | On-going | TBD | NA
1. Effectively engage key stakeholders to maintain, update and articulate UBalt’s unique brand position. | Senior Director Marketing Vice President Advancement Vice President Enrollment Management Partners | On-going | TBD | TBD | Consistent review of our brand position to ensure relevancy.
2. Design and implement a media blitz with intentional positive press releases, advertising, and marketing. | Senior Director Marketing Manager Public Information | Immediate, on-going | Increase marketing budget | Lack of resources | Changing public perceptions of the University | This type of proactive media blitz must be consistent and sustaining for at least 12 months to begin to change public perceptions. At least 40% of this blitz should be in paid advertising and marketing (celebratory ads, info ads etc.), press releases and 60% in targeted strategic communication.
3. Revise and strengthen UBalt's email campaigns that compliments the written communication flow with call-to-action links, for more effective results. | Senior Director Marketing | Immediate, on-going | TBD | TBD | UBalt recognized as the school of choice for career advancement Increased enrollment
4. Develop alumni outcomes marketing campaign. | Senior Director Marketing Asst VP Alumni Relations Asst Director EM Director of Admission | Fall 22 | Alumni Professional photography Funding | Lack of funding | UBalt recognized for career outcomes Outcomes complete and ready for mail and electronic distribution
C. Maintain a cohesive UBalt look and required standards in graduate and undergraduate recruitment and admission marketing and publication designs.
1. Continued redesign of publications to appeal to target audiences (graduate Students, transfer student and young adults) with a modern and fresher look. | Senior Director Marketing Asst Director EM Director of Admission | Immediate and on-going | Continued funding | Lack of financial support | Increased enrollment
2. Create graduate publications to appeal to college and program specific target audiences consistent with UBalt’s brand. | Senior Director Marketing Asst Director EM Director of Admission | Immediate and on-going | May require new funding | Lack of financial support | Increased graduate enrollment | Check graduate enrollment statistics
3. Identify and/or create UBalt traditions to use to build the UBalt brand. | Vice President Student Affairs Vice President Enrollment Management Students Faculty/Staff | Immediate and on-going | TBD | TBD | Increased engagement of Students | Task Force to Advance University Engagement charged
D. Update admission and graduate program websites.
1. Work with Marketing and iFactory web design firm for UBalt's website redesign. | Director of Admission Associate Vice President Enrollment Management Vice President Enrollment Management Associate Vice Provost Director EM Affairs | Immediate and on-going | TBD | TBD | Improved engagement of prospective and current Students. | Increased enrollment

## III RECRUITMENT
III. Recruitment
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
A. Develop an admission funnel, with a robust prospective student, apps, admits and enrolled database.
B. Develop a targeted and strategic communication plan using CRM technology.
C. Increase local and regional constituencies' campus engagement and partnership efforts.
D. Increase transfer student enrollment
E. Increase graduate student enrollment.
F. Increase/maintain first-time undergraduate Students.
G. Increase active-duty military, veteran, and dependent student student enrollment
H. Increase Latino/Hispanic Student Enrollment
I. Increases International Student Enrollment
J. Faculty Recruitment Strategies
K. Increase Yield

## A Admission Funnel
A. Admission Funnel
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
A. Develop an admission funnel, with a robust prospective student, apps, admits and enrolled database.
1. From Task Force Report (Recommendation 6.4c) Design, fund, and implement a clear marketing strategy that ensures that internal and external stakeholders that the University of Baltimore is a four-year undergraduate institution with strong graduate programs and a law school - all of which transform lives. | AVP Enrollment Management Director of Marketing Executive Director of Admission EAB | Immediate and on-going | Funding to generate leads and advertisement | Lack of funding support | Increased number of applications, admits and enrolled | Fall 2022 results Spring 2023 results Fall 24 results
2. Partner with EAB’s Adult Learner Recruitment (ALR) services to increase prospects of graduate and transfer Students. | Vice President Enrollment Management EAB | Completed | NA | NA | Robust graduate and degree completion prospective and applicant pool. | Need to update results from EAB.
3. Find non-traditional first-time undergraduates through Clearinghouse searches, targeted advertisements, and marketing. | Director of Admission Director of Compliance/Operations | On-going | Additional funds for expanded outreach Training | Lack of funding support Lack of training with Clearinghouse searches etc. | Increased application pipelines Increased enrollment of adult first-year Students | This has not been initiated but will be for the fall 24 cycle
4. Create communication campaigns that build and sustain interest in UBalt. | Director of EM Marketing Executive Director of Admission Associate VP Enrollment Management | Immediate and on-going | TBD | TBD | Development of student pipelines | CCBC dual admission program implemented - get number of Students enrolling/Over years
5.Maintain accurate counts and prospect types within the CRM for reporting, planning and enrollment projections. | CRM Manager Director of Compliance/Operations EM Data Analyst | Immediate and on-going | Trained personnel to manage CRM and data | Lack of trained personnel | Ability to use data more accurately for planning and enrollment projections | Data analyst hired CRM manager hired
6. Design and implement a yield communication campaign, which will include continued "recruitment" with extensive marketing and communication after admission. | Director of Office of Admission Associate VP Enrollment Management Asst Director Enrollment Management | On-going | TBD | Funding | Strategic yield campaign developed and deploys | Improved year-over-year yield rate Increased enrollment
7. Establish a recognized UBalt Alumni Recruitment Program for a wider reach in our recruitment efforts. | Associate VP Enrollment Management Director of Admission Admission Counselor Alumni Affairs Rep | Not started | TBD | TBD | Active Alumni recruitment program Increased alumni engagement Increased giving by alumni | We have established a PTK Alumni Program - only one in the MD system.

## B Recruitment-CommPlanCRM
B. Develop a Targeted and Strategic Communication Plan Using CRM Technology
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
B. Develop a targeted and strategic communication plan using CRM technology.
1 Maintain, evaluate, and continuously adjust CRM communication flow for clarity, effectiveness, and efficiency. | CRM Manger Vice President Enrollment Management Associate VP Enrollment Management Assistant Director for Enrollment Management Director for Operations and Strategic Planning | Started and on-going | Hire CRM Manager Hire director of admission Training AVP Admission | TBD but at a minimum funding and OTS resources | Communication campaigns for graduate education, undergraduate educate, colleges and programs
2. Hire an EM communication manager. | Vice President Enrollment Management | Completed | NA | NA | Hired | Hired - Assistant Director EM Communication/Marketing (8/2021) | Hired - Assistant Director EM Communication/Marketing (8/2021)
3. Hire a CRM manager | Associate VP Enrollment Management | Completed |  |  | Hired | Hired - C. Tumey (Get Date) | Hired - C. Tumey (Get Date)
4. Rewrite communication to develop clear and concise communication style that appeals to targeted populations. | Asst Director EM Director of Admission Associate VP Enrollment Management | On-going |  |  | Clear/concise, with call to action communique | All current communication through 2021-2022 was reviewed and updated Annual review and updates | All current communication through 2021-2022 was reviewed and updated Annual review and updates
5 Create communication campaigns that build and sustain interest in UBalt. | Associate Provost Academic Affairs Director of Admission Associate VP Enrollment Management | In progress | Funding if needed | Funding Lack of collaboration and input from key stakeholders | Will become apart of a strategic communication plan | Multiple campaigns have been developed, to include program specific, general UBalt campaigns, grad and UG campaigns, financial aid, and registration campaigns, engagement campaigns. | Multiple campaigns have been developed, to include program specific, general UBalt campaigns, grad and UG campaigns, financial aid, and registration campaigns, engagement campaigns.
6. Document the demographic student profile information for first-time, transfer and graduate Students (including Students within specific Director EM programs) and maintain a corresponding and updated photo library. | Marketing Asst Director EM Marketing | On-going | TBD | TBD | Accurate demographic representation in marketing materials | This has been completed and will be reviewed on as needed in collaboration with Marketing. | This has been completed and will be reviewed on as needed in collaboration with Marketing.
7. Design communication campaigns and messaging about the quality of our five signature programs, highlighting the faculty as exceptional teachers and the successful outcomes of programs using pictorial and articulated results. | Marketing Asst Director EM Marketing | Update for fall 22 On-going | Funding if needed | Funding Lack of collaboration and input from key stakeholders | Targets communique to student Will become part of a strategic communication plan | Need to get updates. | Need to get updates.
8. Design communication plans that address the cost of attendance, financial aid, and scholarships, that include content on the website. | Asst Director EM Marketing Director of Financial Aid Director of Admission | Launched for fall 22 recruitment cycle | TBD | Funding | Easy to understand materials to overcome any enrollment barriers | Completed and updated annually | Completed and updated annually
9. Revise and improve marketing events for all targeted populations. | Asst Director EM Marketing Director of Admission EAB Marketing | On-going | TBD | Funding if needed Lack of collaboration and input from key stakeholders | Improved yield and melt results | Yield comparative data Need to get last three years' yield data. | Yield comparative data Need to get last three years' yield data.
10. Revise and strengthen UBalt's email campaigns that compliments the written communication flow with call-to-action links, for more effective results. | Asst Director EM Marketing EAB Director of Admission | In progress and on-going. Ready for fall 22 recruitment cycle | TBD | Funding if needed Lack of collaboration and input from key stakeholders | Reduce enrollment hurdles Improve enrollment | Enrollment targets and overall enrollment results Year-over-Year comparisons | Enrollment targets and overall enrollment results Year-over-Year comparisons
11. Develop call-to-action text campaigns to direct Students to read emails or written communication. This type of campaign is especially important for transactional communications. | Asst Director EM Marketing Director of Admission Director of Compliance/Processing | On-going | TBD | Texting policies | Texting and messaging fully implemented for effective enrollment results | Open rates Enrollment results | Open rates Enrollment results
12. Manage communication from enrollment related offices for messaging consistency, language, timing, etc. to ensure that prospective and current Students receive coordinated, timely, cohesive, and accurate information. | Associate VP Enrollment Management Asst Director EM Marketing Director of Financial Aid Director of Admission | In progress | TBD | Technical and functional resources In ability to implement advisor link | CRM and Advisor link for enrollment office implemented | TBD | TBD

## C Recruitment-EngagemPartners
C Partnerships and Engagement
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What are the expected outcomes of the task?
C. Increase local and regional constituencies’ campus engagement and partnership efforts.
*1. Develop and implement a plan to strengthen existing and develop new partnerships with local businesses, not-for-profits organizations, and government agencies for student recruitment. | Associate Provost Academic Affairs Deans Director of Admission Associate VP Enrollment Management | In progress | Position to manage developing partnerships | Lack of contacts Funding Models Lack of strategic plans for implementation | Increased numbers of visits to agencies for recruitment for the Baltimore City Scholars Increased numbers of pipelines developed as outlined in task. | Number of Pipelines Created Number of Students enrolled from pipelines Develop new pipelines from college and schools referrals.
2. Strengthen the relationships between UBalt and community colleges. | Director of Admission Associate VP Enrollment Management Assistant Director Enrollment Management Director of Admission Associate VP Enrollment Management | Immediate and on-going | Staffing | Lack of production from targeted CCs Inability to connect with relevant peers at CCs to develop relationships and open pipelines PDs at community colleges engagement in targeted recruitment with UBalt | Increased prospects from targeted community colleges Sign additional dual admission MOUs with other CCs
3. Review and expand articulation and dual enrollment programs both in Maryland and the surrounding regions | Director of Admission Associate VP Enrollment Management | On-going | TBD | TBD | Agreements updated Implementation Plans for all agreements | Other Dual Admission Pipelines Community Colleges Pipelines Enrollment from pipelines New agreements signed with: CCBC Degrees to Succeed enrolled Students since 2022 -69 | The dual admission program with CCBC is not producting the results we hoped for: CCBC D2S Aca Year 20-21 129 0 Aca Year 21-22 96 0 Aca Year 22-23 90 0 Aca Year 23-24 82 1 Aca Year 24-25 83 11 As this data shows as the dual admission program came on board we were not receiving substantant numbers of students via the program and were losing students at an alarming rate without the program. | As a result of this we meet with the CCBC D2S leads to seek any recommendations or concerns they had about the partnership.
4. Determine the potential for growth at the Shady Grove campus and Hagerstown. | Associate Provost for Academic Affairs | In progress | Funding | TBD | Business plan developed and ROI clearly defined Shady Grove recruitment and enrollment plan | Shady Grove enrollment growth
5. Conduct bi-annual school counselor and community college advisor informational programs to message our commitment to UBalt transfer and first-time undergraduates and to celebrate and thank our partners. | Director of Admission | Strategy adjusted and completed | NA | NA | Create pipelines Increased engagement of our admission partners | Transfer Advisory Group established that will hold quarterly meetings
6. Established a recognized UBalt Alumni Recruitment Program for wider reach and alumni involvement in our recruitment efforts | Director of Admission | Spring 25 | NA | NA | Engaged alumni to assist in recruitment efforts | Alumni referral pipeline Increased prospective Students via alumni referrals
7. Revise and improve recruitment events for all targeted populations. | Events Coordinator Director of Admission | On-going |  | Funding | Fewer but more effective events with better attendance | Attendance and evaluation data

## D Recruitment-Transfer
D. Increase Transfer Student Enrollment
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
D. Increase transfer student enrollment.
1. From the task force report:
a. Strengthen the relationships between UBalt and community colleges. | Director of Admission Associate VP Enrollment Management Vice President Enrollment Management | On-going | NA |  | Student pipelines from the community colleges to UBalt | Increased enrollment | Increased enrollment
b. Strategically leverage the Bob Parsons Scholarship to increase the number of new community college graduates and gain transfer student market share. | Vice President Enrollment Management Vice President Advancement | Complete | NA | Donor criteria makes it difficult to award the scholarship | Proposal to adjust criteria for the Parson's scholarship to include parttime Students and new continuing Students | Number of Parson's awards increased. | Number of Parson's awards increased.
c. Focus transfer student recruitment efforts initially on the Community College of Baltimore County, Baltimore City Community College and expand efforts into Anne Arundel, Carroll, Montgomery, and Harford Community Colleges. | Director of Admission Associate VP Enrollment Management | Immediate and on-going | TBD |  | Increased prospects from targeted community colleges Sign additional dual admission MOUs with other CCs Implementation plans for new dual admission agreements | Dual admission agreements signed with Prince George's CC, Increased enrollment | Dual admission agreements signed with Prince George's Community Increased enrollment
2. Establish a community college advisory group. | Director of Admission | Completed | NA | NA | Provide an opportunity for our community college partners to voice any concerns, issues and opportunities to increase enrollment and ensure a smooth transition from the CCs to UBalt | Stronger partners with CCs Increase transfer student enrollment Transfer Advisory Board charged - Howard CC, AACC, BCCC, CCBC, Hagerstown CC, Carroll CC, Frederick CC and PGCC Quarterly meetings at UBal | Stronger partners with CCs Increase transfer student enrollment Transfer Advisory Board charged - Howard CC, AACC, BCCC, CCBC, Hagerstown CC, Carroll CC, Frederick CC and PGCC Quarterly meetings at UBal
3. Explore market options for a multi-faceted transfer student credit articulation portal to secure and implement. | OTS USM Registrar | Completed | NA | OTS resources UBalt ORR resources | ARTSYS Implemented | ARTSYS Implemented | ARTSYS Implemented
4. With the Schaeffer Center, implement an annual Survey of Admitted Transfer Students beginning with the Spring 22 cohort. | Vice President Enrollment Management Schaeffer Center | Completed and on-going | Funding | NA | Survey developed for admitted Students across all student careers, except law. | Survey administered fall 22 and spring 23, Fall 24 To be administered - Spring 25 | Survey administered fall 22 and spring 23, Fall 24 To be administered - Spring 25
5. Review current transfer student services and programs for effectiveness and efficiencies. | Associate Vice President Enrollment Management Vice President Student Success Director of Admission | On-going | SEMC | NA | Identify enrollment and retention barriers and remove | Increased enrollment of new and continuing Students. | Increased enrollment of new and continuing Students.
6. Develop specialized transfer publications and communication campaigns. | Asst Director EM Marketing Director of Admission Associate VP Enrollment Management | Fall 22 and on-going |  |  | Transfer student communication campaigns | Increased Enrollment | Increased Enrollment
7. Review and expand articulation and dual enrollment programs both in Maryland and the surrounding regions. | Director of Admission Deans Department chairs Transfer Coordinator | Immediate and on-going | TBD | TBD | Complete review of agreements for relevancy and updates Develop strategic enrollment plans for MOUs | Pipeline for applicants Increased enrollment | Pipeline for applicants Increased enrollment
8. Expand our community college visits locally and regionally. | Director of Admission | Fall 21 and on-going | TBD |  | Improved relationships and stronger partnerships with CC partners | Analysis of effectiveness of community college visits (# of enrollments) Increased enrollment | Analysis of effectiveness of community college visits (# of enrollments) Increased enrollment
9. Develop a unified transfer student website. | Senior Director of Marketing Asst Director EM Marketing Web Design firm | TBD by timeline of web design firm. | Web design firm | TBD | Marketing and informational website for transfer Students | Increased enrollment | Increased enrollment
10. Develop and implement, in collaboration with CC partners, a dual admission program. | Director of Admission Associate VP Enrollment Management Deans | On-going | TBS | TBD | Dual Admission pipelines established. | Outcomes from CCBC partnership (fall 24) 2-3 new partnerships Increased transfer enrollment | Outcomes from CCBC partnership (fall 24) 2-3 new partnerships Increased transfer enrollment
11. Increase scholarship dollars for transfer Students and on-going review of strategic policies to award new and current scholarships | Director of Financial Aid Vice President Advancement | On-going | TBD | Funding | Increased funding | Lower loan indebtedness Increased transfer student enrollment | Lower loan indebtedness Increased transfer student enrollment
12. Develop Phi Theta Kappa recruitment strategies | Director of Admission | On-going | TBD | TBD | PTK Alumni Recruitment Program Targeted PTK specific visits at CC Targeted communication campaigns Open alumni panels | Increased transfer enrollment | Increased transfer enrollment
13. Replace state scholarships for transfer Students suspended fall 24 and spring 25 | Director of Financial Aid Vice President Enrollment Management CFO | On-going | Funding to replace new transfer and continuing student Rawlings State Grant | Funding | Reinstatement of state grants with institutional funds | Regain transfer market that received Rawlings grant. | Regain transfer market that received Rawlings grant.

## E Recruitment-Graduate
E. Increase Graduate Student Enrollment
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
E. Increase graduate student enrollment.
1. Partner with EAB to develop an adult student prospect pool to create a higher level of sophistication with search engine program digital marketing and volume capability. | Vice President Enrollment Management EAB Director of Admission Director of Compliance/Processing | Completed | NA | NA | Increases across the funnel. | Increase enrollment
2. Complete Portfolio Health Check with EAB | EAB Associate Provost Academic Affairs Vice President Enrollment Management | Annual Portfolio Health Check | TBD | Using the data to determine where to focus our recruitment efforts | Completed Portfolio health check Use the data to strategize new graduate enrollment | Increased enrollment On going planning and assessment tool
3. Increase resources for graduate recruitment and admission in the colleges, graduate admission office and the University's marketing department. | Provost Office Vice President Enrollment Management CFO | On Hold | TBD | Lack of funds due to declining enrollment Budgetary restraints | More effective enrollment effort | Increased enrollment
4. Develop a high touch communication plan for graduate prospective Students including social media, email, text, and other digital marketing methods. | Associate VP Enrollment Management Assistant Director EM Marketing Director of Admissions Departments | On-going | TBD | TBD | Individual program campaigns College and school campaigns Graduate education campaigns | Increased enrollment
5. Ensure immediate responses to inquiries from graduate Students. | EAB Associate Director of Graduate Admission Assistand Director EM Marketing | On-going | TBD | Reduced staffing | 24-48 Hours response turnaround rate | Increased yield of graduate Students across the admission funnel
6. Review the admission and enrollment processes for graduate students ensuring quick decision turnaround throughout the admission funnel. | Associate Provost Academic Affairs Associate VP Enrollment Management Director of Admission Assistant Director EM Communication Departments Program Directors Associate Director Graduate Admission | Implement process for spring 26 decisions and ongoing | TBD | TBD | Graduate admission decisions within 24 hours Improved application and admission processes to facilitate quicker decisions | Increased enrollment
7. Maintain and highlight as part of a communication and marketing campaign, term, and modality flexibility options, face-to-face student service options, early evening office hours etc., that cater to the adult and returning student at UBalt. | Senior Director of Marketing Assistant Director EM Communications Colleges/Schools Associate Direcrtor of Graduate Admission Associate Vice President Enrollment Management | On-going | TBD |  | Increases across the admission funnel Marketing options that highlight UBalt's flexibility and on-campus opportunities | Increased enrollment
a. Build and offer more full online programs. | Provost Deans | On-going | Funding for technology and faculty | Lack of funding support | Increased in fully online programs | Increased enrollment
b. Build and offer more full evening programs. | Provost Deans | On-going | Funding for technology and faculty | Lack of funding support | Increase full evening programs
c. Evaluate in-person weekend hybrid modes of program availability | Provost Deans | On-going | Funding for technology and faculty | Lack of funding support
d. Grow summer school programs and offerings so that UBalt can offer year-round enrollment at UBalt. | Provost Deans | On-going | Funding for technology and faculty | Lack of funding support | Robust summer school offerings Market to local Students returning to the summer to take courses at UBalt
6. Promote, and market seamless pathways to graduate programs for undergraduate Students. | Senior Director of Marketing Associate Director Grad Admission Director of Admission Associate VP Enrollment Management | On-going | TBD | TBD | Increase number of undergraduate Students into the graduate programs | Increased enrollment
8. Auto-admit current UBalt undergraduates who qualify into UBalt graduate programs. | Associate VP Enrollment Management Director of Compliance/Processing Program Directors ITS | Not Started | System set-up to auto admit | TBD | Increase admits | Increase enrollment
9. Design and implement a recruitment campaign for Ubalt’s alumni who graduated in the last 5 years to encourage them to enroll into another acAsst Director EM Marketingic degree program at Ubalt. | Alumni Services Associate VP Enrollment Management Director of Admission | Immediate and on-going | TBD | TBD | Improved alumni engagement and possible giving. Increased applications for graduate programs | Increased enrollment
10. Develop and increase the number of 3+2 agreements to increase both undergraduate and graduate enrollment. | Associate VP Enrollment Management Program Directors | Immediate/On-going | TBD | TBD | Increase numbers across the admission funnel | Increased enrollment
11. Increase graduate student financial assistance and develop a scholarship strategy for graduate scholarships. | Director of Financial Aid Associate VP Enrollment Management | On-going | TBD | TBD | Reduce the amount of loans graduate Students have to take | Increased enrollment
12. Engage the colleges’ alumni boards and other alumni in the recruitment process. | Vice President Advancement Associate Vice President for Enrollment Management Alumni Services | On-going | Alumni recruitment guidelines and activities | TBD | Increased alumni engagement Increased scholarship giving YouTube Videos In-person interviews Recruitment programs | Increased enrollment
13. Update graduate programs web pages with specific information graduate Students are researching | Senior Director Marketing Marketing Associate Provost for Academic Affairs Program Directors | On-going | New University Website | TBD | Program page updates to highlight program time to completion, costs, professional outcomes, and contact information. | Efforts underway to update program pages by departments Increased prospects and enrolled Students.
14. Design and implement a yield communication campaign, which will include continued "recruitment" with extensive marketing and communication after admission. | Associate Vice President Enrollment Management Assistant Director EM Communication/Marketing | On-going | TBD | Funding | Strategic yield campaign developed and deployes | Improved year-over-year yield rate Increased enrollment
15. Remain active in the National Association for Graduate Enrollment Management NAGAP, a national organization that provides resources on the best practices in graduate enrollment management and professional development opportunities. | Associate VP Enrollment Management Director of Admission Associate Director Graduate Admission | Current and on-going | Paid membership | Costs | Professional development opportunities to remain current in the graduate market Networking and support with colleagues Attend programs for prospective Students | Increase enrollment

## F Recruitment-FirstYear
F. Increase/Maintain First-Time Undergraduate Students
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
F. Increase/maintain first-time undergraduate Students.
1. From Task Report
a. Promote and recruit for the Helen P. Denit Honors program | Director of Honors Program Associate Vice President Enrollment Management Director of Admission | In progress | Funding for programming | Lack of traditional campus Not enough scholarships for higher achieving Students | Increased numbers of honor Students | See task force final report for more details (Recommendation 3, 3.4a) Increased enrollment
b. Promote and recruit for UBalt’s bachelors’/masters’ programs including the early entry law program. | Marketing Associate Vice President Enrollment Management Assistant Director EM Communication/Marketing | Immediately and on-going | Funds | TBD | Strategic Recruitment Plan for bachelors'/masters' programs | Increased number of bachelor's to Master's programs Increased enrollment
c. Create and implement a recruitment plan to enroll new first-time student cohorts into UBalt’s five signature areas of excellence. | Associate Vice President Enrollment Management Director of Admission Assistant Director EM Communication/Marketing | Need to review and update plan annually | Funding for strategies | Lack of traditional campus Not enough scholarships for higher achieving Students | Targeted increased enrollment into the five signature areas | Increased enrollment
2. Explore the potential dual enrollment option for freshmen not directly admissible into UBalt. | Associate Vice President Enrollment Management Director of Admission | Current and on-going as part of the task force report | TBD | Policies that may be conflict | Engagement of HS Students Pipeline | Increased enrollment
*3. Create communication campaigns that build and sustain interest in UBalt. | Associate Provost Academic Affairs Director of Admission Associate VP Enrollment Management | In progress | Funding | TBD | More robust prospective pool to move Students through the funnel | See II-A Increased enrollment
4. Create profiles of those who will likely enroll and buy the names of Students who fit our profile. | Vice President Enrollment Management Schaeffer Center Associate Vice President Enrollment Management EM Data Analyst | Current and on-going | Funding | TBD | More robust prospective pool to move Students through the funnel Profiles developed | Increased enrollment
5. Develop a strategic communication plan with multiple levels of engagement. | Assistant Director EM Communication/Marketing Director of Admission Vice President Enrollment Management Associate Vice President Enrollment Management Marketing EAB | In progress | NA | TBD | Strategic communication campaigns for new Students Strategic communication campaigns for programs | See II-B Increased enrollment
6. Build stronger relationships with local counselors to break down misconceptions about UBalt’s commitment to first-time undergraduate Students. | Director of Admission Vice President Enrollment Management | Current and on-going | NA | TBD | Improved relationships, that will lead to improved perceptions Improved engagement Increased enrollment | Increased enrollment
7. Revise and improve marketing events for all targeted populations. | Director of Admission | Not started, but a transfer advisory board is active and meeting | Funding for meetings | NA | Forum to address issues, learn what's new at UBalt, suggestions on how we improve processes and procedures for applying and enrolling first-time undergraduate. | Increased enrollment
8. Revise and strengthen UBalt's email campaigns that compliments the written communication flow with call-to-action links, for more effective results. | Associate VP Enrollment Management Director of Admission | In progress | Replacement of funds for travel and recruitment that has been used to cover other needs | COVID Restrictions Remaining virtual, without face to face interactions with Students | Preserve and increase our market Increased enrollment
9. Strategically leverage first-time undergraduate financial aid and scholarships for best return in enrollment. | Director of Financial Aid Vice President Enrollment Management Associate Vice President Enrollment Management | On-going | TBD | TBD | Lower loan indebtedness | Increase enrollment
10. Increase the number of dual enrolled Students who enroll into UBalt | Associate Vice President Enrollment Management Director Early College Initiatives Director of Admission | On-going | TBD | TBD | Number of Students from the dual enrollment program at UBalt who enroll into UBalt | Increase percentage enrollment from 1.3% to 5% over 3 years
11. Registrar dual enrolled Students before census, so those number count as headcount | Director Early College Initiatives Registrar's Office ITS | On-going |  | Lack of technology to eliminate manual processing | Dual enrolled Students registered before census | Total year-over-year enrollment increased with dual enrolled

## G Recruitment-Military
G. Increase Active-Duty military, Veteran, and Dependent Student Enrollment
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
G. Increase active-duty military, veteran, and dependent student enrollment.
1. Assess and meet (where we can) the higher education needs of the military community. | Bob Parson Veteran Center Vice President Student Success Director of Admission | By spring 22 and on-going | TBD | TBD | Strategic recruitment and retention plan to increase new and continuing military and military related Students | Increased military enrollment
2. UBalt’s Office of Admission will partner with the Bob Parsons Veteran’s Center to leverage existing resources to understand the specific needs of veterans and their military family’s members to recruit them. | Bob Parson Veteran Center Vice President Student Success Associate Vice President Enrollment Management Director of Admission | Immediate and on-going | TBD | TBD | Identify available resources | Increased military enrollment
3. Expand and develop innovative delivery systems to provide offerings that respond to specialized schedules and calendars of military personnel. | Associate Provost Academic Affairs Deans Bob Parsons' Veteran Center | On-going | TBD | TBD | Innovative delivery of programs and services for active duty and military affiliated Students. | Increased military enrollment
4. Move veteran's certification to the registrar's office for timely and effective services | Office of the Registrar | Completed | TBD | TBD | Improved customer service to veterans | Increased military enrollment
*5 Create communication campaigns that build and sustain interest in UBalt. | Associate Provost Academic Affairs Director of Admission Associate VP Enrollment Management | Immediate and on-going | TBD | TBD | Identify veteran enrollment barriers and solutions | Increased military enrollment
6. Partner with military bases’ Education Centers and transitional programs to offer courses, professional development, and workshops. | Colleges and Schools Bob Parsons Veteran Center | Immediate and on-going | TBD | Access to military bases Proximity to UBalt | Innovative delivery programs and services for active duty and military affiliated students. | Increased military enrollment
7. Feasibility study on accepting more prior military experience for credit (using ACE’s equivalencies). | Associate Provost Deans | Immediate and on-going | TBD | TBD | Feasibility student complete and decisions made - what decisions have been made? | Increased military enrollment
8. Expand graduate program offerings for military officers. | Associate Provost for Academic Affairs Deans Bob Parson's Veteran Center | Immediate and on-going | TBD | TBD | Specialized accelerated programs. | Increased military enrollment

## H Recruitment-HispanicLatino
H. Increase Latino/Hispanic Student Enrollment
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
H. Increase Latino/Hispanic Student Enrollment
1. Develop a comprehensive undergraduate and graduate recruitment and enrollment plan for the Latino/Hispanic population. | Vice President Enrollment Management Associate Vice President Enrollment Management Director of Admission | TBD | Bilingual | Lack of specialized experience in this area Supreme Court ruling on diversity recruitment and admission | Plan developed and strategies being implemented. | Increased Latino/Hispanic enrollment | Increased Latino/Hispanic enrollment

## I Recruitment-International
I. Increase International Student Enrollment
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
I. Increase International Student Enrollment.
1. Assess UBalt’s ability and capacity for an increased international student presence. | Provost Associate Provost Deans Vice President Student Success Associate VP Enrollment Management International Senior Grad Counselor | Immediate | NA | TBD | International student enrollment plan | A full plan has not been developed however there has been exploration
2. Identify new recruitment territories/segments based on data, trends and country specific characteristics like economic status/stability, student sponsorship, mobility etc. | Director of Admission International Senior Grad Counselor Associate VP Enrollment Management EAB EM Data Analyst | Immediate | NA | TBD | Strategic direction to recruit international Students | Increased enrollment of international Students
3. Develop and expand the 3+2 programs with International Institutions. | Associate Provost Academic Affairs Deans Associate Vice President Enrollment Management International Senior Grad Counselor | Immediately | TBD | TBD | Increased number of 3+2 programs Increased enrollment | Increased enrollment of international Students
4. Hire agents in key markets to recruit and enroll Students. | Associate VP Enrollment Management Associate Provost Academic Affairs International Senior Grad Counselor | Immediately |  | Payment options | Established guidelines and UBalt specific contract ready for deployment Signed contracts and hired agents | Increased enrollment of international Students
*5 Create communication campaigns that build and sustain interest in UBalt. | Associate Provost Academic Affairs Director of Admission Associate VP Enrollment Management | Immediately | NA | TBD | Reduce enrollment hurdles Improve enrollment | Increased enrollment of international Students
6. Expand E-Recruitment strategies – Web and Social Media that are mobile compatible and culturally accurate (i.e., translations, measurements etc.), should include “How to Videos”, FAQ, customized pages based on location, and remain current on worldwide social networking sites, live chat, virtual fairs and campus tour. | International Senior Grad Counselor International Student Services Assistant Director EM Communication/Marketing Director of Admission | Immediate and on-going | Funding | Funding | Increase number of viable international prospective Students | Increased enrollment of international Students
7. Targeted advertising/publications– essential to develop brand and advertising strategies targeted to international Students | Assistant Director EM Communication/Marketing Marketing Director of Admission | In progress and on-going | Funding |  | Marketing and communication campaigns targeted for international Students | Increased enrollment of international Students
8. Target and recruit international Students who are already living in the United States. | International Senior Grad Counselor International Student Services Director of Admission | In progress | Funding | Funding Strategies to locate pipelines of international Students already in US. | Increased numbers of prospective international Students | Increased enrollment of international Students
9. Revise and improve marketing events for all targeted populations. | International Senior Grad Counselor International Student Services Director of Admission | Immediate and on-going | Funding | Funding Strategies to locate pipelines of international Students already in US. | Build prospect pool Increase enrollment | Increased enrollment of international Students

## J Recruitment-Faculty
J. Faculty Involvement
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
J. Faculty Involvement
1. Focus and create avenues to showcase faculty achievements and research such as social media sites, the website and with targeted campaigns etc. From EAB 1. Conduct faculty and instructors interviews and broadly release profiles, stories and videos. 2. Secure interview and guest spots for faculty on free public facing media channels. 3. Showcase faculty profiles, achievements, expertise and other news updates UBalt's website homepage and on each program college, school and/or program website. 4. Increase faculty social media use and provide training. 5. Host community campus events as an opportunity to showcase faculty expertise. 6. Host podcasts with rotating faculty and instructor expert guests. 7. Create a electronic newsletter or magazine for the public that highlights faculty expertise and achievements. 8. To reduce stealth prospects, offerStudents incentives to provide contact information. 9. Provide access to chat with a live chat advisor. | Associate Provost for Academic Affairs Deans Program Directors Director of Admission Assistant Director EM Communication/Marketing Associate Vice President Enrollment Management | Immediately | Funding Faculty volunteers | Lack of funding support Lack of faculty volunteers | Faculty storytelling profiles developed and posted and reposted on social media, the website etc. Faculty communication campaigns developed and deployed Enhanced faculty presence to prospective Students and applicants Enhanced Director EM Marketing reputation of UBalt | Increased enrollment
2. Continous competitive market reviews and health checks to provide information to make informed decisions concerning UBalt’s capacity, to verify and/or contradict anecdotal data and stories and test our assumptions against market trends and benchmarks. | EAB Director EM Health Check Vice President Enrollment Management Provost Deans | On-going | TBD | TBD | Use information to make decisions on how to target programs for recruitment | Increased enrollment
3. Increase options for learning pathways such as dual-degree, certificates, accelerated programs | Provost Deans Vice President Enrollment Management | Immediate and on-going | TBD | TBD | More options for returning adults Increased enrollment Faster degree completion options | Increased enrollment
4. Continue participation in recruitment and admission activities for undergraduate and graduate programs. | Academic Program Directors Admission Events Coordinator Director of Admission | On-going | Funding | Lack of funding support Lack of faculty volunteers | Increased participation in recruitment events | Increased enrollment
*5 Create communication campaigns that build and sustain interest in UBalt. | Associate Provost Academic Affairs Director of Admission Associate VP Enrollment Management | On-going | NA | Faculty availability | Increased enrollment | Increased enrollment
6. Align UBalt faculty speakers with signature areas of excellence to travel to high schools, community colleges and select four-year institutions for classroom lectures/workshops. | Associate Provost Academic Affairs Deans Associate Vice President Enrollment Management Director of Admission | Spring 23 and on-going | Funding | Faculty participation | Increased enrollment Expanded positive exposure
7. Coordinate and collaborate with the office of admission on recruitment activities and create a calendar of college/school/department activities. | Program Directors Assistant Director EM Communication/Marketing | Immediately | We may need software or training on any current software the university uses. | TBD | Master calendar of Director EM Marketing recruitment, outreach, community service events. | Increased participation in events Increase enrollment
8. Provide annual training for recruitment staff. | Deans Associate Vice President Enrollment Management Director of Admission | Training for following fall to happen in May, after graduation | TBD | Timing Faculty availability to train and update admission staff | Cross-trained admission staff with accurate information for recruitment | Increased enrollment

## K Recruitment-Yield
K. Increase Yield
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Outcomes | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
K. Increase Yield
1. Improve our brand and image (see II Branding, Image and Marketing).
* 2. Establish an Enrollment Barriers task force to Improve the enrollment process and eliminate confusing communications and unintentional administrative barriers. | Associate VP Enrollment Management Vice President Student Success | April 2023 subcommittee charged | NA | NA | Task Force empowered to identify and recommend solution to enrollment barriers. Initial barriers identified Continued identification via the Student Success Council | Fewer enrollment barriers Less complaints Improved enrollment Provost Office created the Student Success Council
3. Design and implement a yield communication campaign, which will include continued "recruitment" with extensive marketing and communication after admission. | Marketing Assistant Director EM Communication/Marketing Associate Vice President Enrollment Management Director of Admission | On-going |  | Funding | Strategic yield campaign developed and deployed | Improved year-over-year yield rate Increased enrollment
4. Continuous engagement with Students with the use of departmental strategic communication plans. | Colleges and Schools | On-going | TBD | Lack of resources | College, School, department and program level communication campaigns for yield | Improved year-over-year yield rate Increased enrollment
*5 Create communication campaigns that build and sustain interest in UBalt. | Associate Provost Academic Affairs Director of Admission Associate VP Enrollment Management | On-going | Funding | Lack of funding Lack of data | Outcomes pieces developed | Improved year-over-year yield rate Increased enrollment
6. Develop semi-annual community college days at UBalt (instant admission decisions). | Director of Admission Coordinator of Admission Events Associate Vice President Enrollment Management | Not yet started | Program funding |  | Community College Days scheduled | Improved year-over-year yield rate Increased enrollment

## IV AFFORDABILITY
IV. Affordability
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Objectives | Results | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
A. Strategic Use of Financial Aid
1. Determine how we should leverage our limited funds to meet our enrollment goals, better assist Students financially and lower their loan indebtedness. | Director of Financial Aid Vice President Enrollment Management Associate VP Enrollment Management Director of Admission | On-going | TBD | TBD | Less student indebtedness Increased enrollment
3. Replace state scholarships for transfer Students suspended fall 24 and spring 25 | Director of Financial Aid Vice President Enrollment Management CFO | On-going | Funding to replace new transfer and continuing student Rawlings State Grant | Funding | Reinstatement of state grants with institutional funds | Regain transfer market that received Rawlings grant.
4. Move the management and awarding of MSB foundation scholarships to EM. | Vice President Enrollment Management Director of Financial Aid Associate VP Enrollment Management Director EM Systems/Compliance | Spring 2024 - planning and implementation | Funding 1 position | Resources | To increase enrollment with Foundation Scholarships Strategic use of scholarships for recruitment and retention | Reduction in the amount of foundation funds that are not spent Scholarships consistently awarded
5. Work with advancement to increase the number of scholarships for new graduate and undergraduate Students. | Vice President Advancement President Provost Vice President Enrollment Management | Immediate and on-going | TBD | Reluctant donors Lack of strategic scholarship awarding for recruitment and retention | Strategic use of scholarships for recruitment and retention Increase donations More scholarships | Enrollment
6. Development an awarding strategy for 1M+ increase state funding for scholarships. | Director of Financial Aid | Completed and on-going review. | NA | TBD | Increased enrollment and persistence | Funding awarded
B. Improve student services and educational programming to include financial literacy.
7. Revise and improve marketing events for all targeted populations. | Director of Financial Aid Associate VP Enrollment Management Vice President Student Success | Immediate and on-going | TBD | Lack of funding | Financial Literacy programs | Enrollment (new and retention)
8. Revise and strengthen UBalt's email campaigns that compliments the written communication flow with call-to-action links, for more effective results. | Vice President Enrollment Management Associate VP Enrollment Management Vice President Student Success | Immediate and on-going | TBD | TBD | Remove barriers to new and continued enrollment Ensure Students have positive experiences at the University | Fewer complaints Improved retention rates, lower and attrition numbers Increased enrollment
9. Cross-train admission staff in aspects of financial aid to support the work of the financial aid office. | Associate VP Enrollment Management Director of Admission Director of Financial Aid | In progress and on-going | TBD | Lack of time Resistance to change Job security concerns | Improved enrollment experience for prospective and continuing Students | Financial Aid and Admission Offices have been combined Fewer complaints

## V INFRASTRUCTURE
V. Infrastructure
RECRUITMENT AND ENROLLMENT ACTION PLAN University of Baltimore Updated 2/11/2025 | Responsible | Deadline | Resources | Potential Barriers | Objective | Results/Notes | Assessment
What task will be done? | Who will do it? | By when? | What do you need to complete this step? (People, money, tools, etc.) | What could get in the way of task completion? How will you overcome them? | What is the outcome of the task?
A. From Task Force Report
1. Realign and deploy resources within Enrollment Management to focus on UBalt’s stated target student populations for recruitment and retention. | Vice President Enrollment Management | On going | TBD | Administrative policy barriers | More effective and efficient services | See task force final report, recommendation (2) 2.5
B. Sufficiently staff offices whose primary responsibility is enrollment and enrollment related offices. | Vice President Enrollment Management Associate VP Enrollment Management Director of Admission Director of Financial Aid | Current and on-going |  | Lack of funding support | Well staffed offices to implement recruitment plan and increase enrollment with trained personnel | Increased enrollment Number of staff hired
1. Restructure the EM Division for better use of staff and more cross training across the division. | Vice President Enrollment Management Associate VP Enrollment Management | Completed on-going review and adjustments as needed |  | Resistance to change | Offices of Admission and Financial Combined Critical leadership positions created and hired | AVP, Executive Director of Admission, Associate Directors hired or promoted with no additional funding.
C. Improve enrollment processes for efficiency and effectiveness.
1.Create communication campaigns that build and sustain interest in UBalt. | Associate Provost Academic Affairs Director of Admission Associate VP Enrollment Management | TBD | Funding for software, possible consultant One position to oversee one-stop, social media and the campus tour | TBD | Revised date to coincide with new web design and implementation
2. Continuous training and cross-training of EM employees. | Vice President Enrollment Management Associate VP Enrollment Management Director of Admission Director of Financial Aid | In progress Training sessions scheduled by Spring 22 - Check on this - did it happen | Need external and internal training | Lack of collaboration and willingness for training | More efficient and effective student communication with staff properly trained. | Annual training sessions for EM staff internally and with external units Check on when and how often the training sessions take place.
3. Raise the level of expectation for individual attention and customer service for enrollment purposes and train the UBalt community to meet expectations. | Vice President Enrollment Management Associate VP Enrollment Management Director of Financial Aid Director of Admission | Immediate and long-term | TBD | TBD | Collaborative planning meetings Training sessions developed Customer service measures developed | Improved student experiences based on outcomes from established measures
4. Develop priority deadlines that allow students to receive a prompt decision, financial aid package and early opportunity to register for classes. | Associate VP Enrollment Management Director of Admission Director of Financial aid | Immediate and continuous | TBD | Fall 24 awarding issues because of changes to the FAFSA, PELL eligibility and ISIR receipt | Deadlines established | What are the deadlines?
5. Revise and improve marketing events for all targeted populations. | Bursar Director of Financial Aid | Immediate and continuous | TBD | TBD |  | Some of this work will occur in the enrollment barriers task force.
6. Revise and strengthen UBalt's email campaigns that compliments the written communication flow with call-to-action links, for more effective results. | Director of Admission Assistant Director of EM Communication/Marketing | Completed for fall 22 | NA | NA | Letters and inserts edited | Requires annual review
7. Collaboration with advising to further develop our student experience from admission to advisement and registration. | Associate Provost for Academic Affairs Vice President Enrollment Management Vice President Student Success Deans | Fall 21 | TBD | TBD | TBD | TBD
8. Continuous review of processes, procedures, and policies for possible obstacles to enrollment. | Vice President Enrollment Management Associate VP Enrollment Management Director of Admission | In progress | TBD | TBD | Remove enrollment barriers to increase overall enrollment | After the work of the Enrollment Barriers Task Force, EM will ensure that processes remain up to date
D. Create a “Front Door” to The University of Baltimore
1. Coordinate efforts to create a welcome center space. | Vice President Advancement Vice President Enrollment Management | On going | TBD | Lack of funding support to create the one-stop | Present a professional and modern UBalt first impression. | Welcome Center Opening Fall 24
2. Within the new webpage, create a UBalt Welcome Center Portal, to showcase the campus, our Students, and the ease of the enrollment process from application to enrolled student. Some of the items the portal would include are a virtual tour, student videos, webcasts (pre-tour talk, financial aid workshops etc.) | Asst Director EM Associate VP Enrollment Management Director of Admission Director of Financial Aid | Not Started | Web design firm |  | Portal live YouVisit Tour to create a professional virtual tour | Increased enrollment Comparative data on tour participates