Middle States Commission for Higher Education Reaffirmation of Accreditation Timeline 2023– 2026.

While developing Self-Study continue institutional effectiveness plans, including gathering and aligning the Strategic Plan and all divisional and unit plans. Updated November 12, 2023.

**Dates Activity/Task**

|  |  |  |
| --- | --- | --- |
| **Dates** | **Activity/Task** | **Status** |
|  |  |  |
| **January and February 2023** | Share timeline and updates for Self- Study with campus community  | Complete |
| **February 2023** | Gap Analysis | Ongoing |
| **February- April 2023** | Identify data leads per division. Develop site and Annotated Bibliography  | Complete |
| **April-May 2023** | Update current Strategic Plan and Board of Regents Task Force report action items | Complete |
| **Summer 2023** | Continue above and develop action plan for all units based on gap analysis. Update current Strategic Plan and Board of Regents Task Force report action items | In process |
|  |  |  |
| **October 2023** | Self-Study Institute  | Complete |
| **November /December 2023** | Assemble Steering Committee Working Group and Steering Committee Meet and Greet Remote Meeting with Commission Staff Liaison, Begin Self-study Design (SSD) Develop charge and template for work groups  | Complete |
| **February/March 2024**  | Submit draft SSD by Ma toCommission Staff Liaison, Possible Site Visit on April 11. 2024 Begin Institutional Compliance Form   |  |
| **April 2024** | Submit SSD to MSCHE VP April 10 2024Campus visit April 25th 8 am – 1 pmRevisions and Acceptance of the SSD Develop communication plan |  |
| **April 2024 – June 2024** | Phase I: Evaluating Compliance to the Standards Working Groups gather and analyze data and submit progress reports to Steering Committee  |  |
| **April 2024 – October 2024** | Phase II: Evaluating Alignment of the Standards to the College’s Institutional Priorities Working Groups gather and analyze data and submit progress reports to Steering Committee  |  |
| **October 2024 – January 2025** | Phase III: Final Working Group Report Working Groups report on any outstanding lines of inquiry and/or evidence  |  |
| **January 2025 – May 2025** | MSCHE Team chair chosen MSCHE Visit date chosen Accepted SSD sent to Chair Steering Committee reports to Chair, Co-chair and writers Self-Study drafted and shared with campus community   |  |
| **May 2025 – September 2025** | Self-Study revisions and campus review  |  |
| **September 2025 – November 2025**  | Self-Study report draft sent to Team Chair Team Chair’s preliminary visit  |  |
| **December 2025 – January 2026** | Self-Study Report finalized based on Team Chair feedback and shared with the campus community  |  |
| **February 2026 – March 2026** | Final Self-Study/Evidence Inventory uploaded to MSCHE Portal Evaluation Team on campus Team report Institutional response   |  |
| **June 2026** | Commission meets to determine action   |  |
| **July 2026** | Respond in writing to MSCHE report  |  |
| **Fall 2026** | Implementation Plan for Follow up  |  |
|  |  |  |