Middle States Commission for Higher Education Reaffirmation of Accreditation Timeline 2023– 2026.

While developing Self-Study continue institutional effectiveness plans, including gathering and aligning the Strategic Plan and all divisional and unit plans. Updated November 12, 2023.

**Dates Activity/Task**

|  |  |  |
| --- | --- | --- |
| **Dates** | **Activity/Task** | **Status** |
|  |  |  |
| **January and February 2023** | Share timeline and updates for Self- Study with campus community | Complete |
| **February 2023** | Gap Analysis | Ongoing |
| **February- April 2023** | Identify data leads per division. Develop site and Annotated Bibliography | Complete |
| **April-May 2023** | Update current Strategic Plan and Board of Regents Task Force report action items | Complete |
| **Summer 2023** | Continue above and develop action plan for all units based on gap analysis. Update current Strategic Plan and Board of Regents Task Force report action items | In process |
|  |  |  |
| **October 2023** | Self-Study Institute | Complete |
| **November /December 2023** | Assemble Steering Committee  Working Group and Steering Committee Meet and Greet  Remote Meeting with Commission Staff Liaison,  Begin Self-study Design (SSD)  Develop charge and template for work groups | Complete |
| **February/March 2024** | Submit draft SSD by Ma to  Commission Staff Liaison, Possible Site  Visit on April 11. 2024  Begin Institutional Compliance Form |  |
| **April 2024** | Submit SSD to MSCHE VP April 10 2024  Campus visit April 25th 8 am – 1 pm  Revisions and Acceptance of the SSD  Develop communication plan |  |
| **April 2024 – June 2024** | Phase I: Evaluating Compliance to the Standards Working Groups gather and analyze data and submit progress reports to Steering Committee |  |
| **April 2024 – October 2024** | Phase II: Evaluating Alignment of the Standards to the College’s Institutional Priorities  Working Groups gather and analyze data and submit progress reports to Steering Committee |  |
| **October 2024 – January 2025** | Phase III: Final Working Group Report  Working Groups report on any outstanding lines of inquiry and/or evidence |  |
| **January 2025 – May 2025** | MSCHE Team chair chosen  MSCHE Visit date chosen  Accepted SSD sent to Chair  Steering Committee reports to Chair, Co-chair and writers  Self-Study drafted and shared with campus community |  |
| **May 2025 – September 2025** | Self-Study revisions and campus review |  |
| **September 2025 – November 2025** | Self-Study report draft sent to Team Chair Team Chair’s preliminary visit |  |
| **December 2025 – January 2026** | Self-Study Report finalized based on Team Chair feedback and shared with the campus community |  |
| **February 2026 – March 2026** | Final Self-Study/Evidence Inventory uploaded to  MSCHE Portal  Evaluation Team on campus  Team report  Institutional response |  |
| **June 2026** | Commission meets to determine action |  |
| **July 2026** | Respond in writing to MSCHE report |  |
| **Fall 2026** | Implementation Plan for Follow up |  |
|  |  |  |