## Summary
Count of Edit Action | Column Labels
Row Labels | Dagemawit Kebede | Grand Total
Completed Edit | 154 | 154
2nd Review Completed | 63 | 63
Marketing | 2 | 2
Grand Total | 219 | 219

## Full Plan
Content Lead | Group | Reviewer/Editor | Review/Edit Status | Priority | iFactory Destination | Source | Destination | Page Template | Migration Action | Edit Action | Planner Tracker | Notes | Source URL 1 | Page Notes | Notes | Source URL 4 | Source URL 5 | Source URL 6 | Source URL 7 | Source URL 8 | Source URL 9 | Source URL 10 | Source URL 11 | Source URL 12 | Source URL 13 | Source URL 14 | Source URL 15 | Source URL 16
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Main > > > > | ubalt.edu/campus-life/engagement | /Student-Life/index.cfm | Landing | Migrate | Keep (Revise) | iFactory Outline |  | ubalt.edu/campus-life/engagement | ubalt.edu/campus-life/engagement/virtual-events.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Get Involved > Main > > > | ubalt.edu/campus-life/engagement/student_activities.cfm | /Student-Life/Get-Involved/index.cfm | Interior | Migrate | Keep (As Is) | iFactory Outline |  | ubalt.edu/campus-life/engagement/student_activities.cfm | ubalt.edu/campus-life/performing-arts.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Get Involved > Student Organizations > > > | ubalt.edu/campus-life/engagement/student_organizations.cfm | /Student-Life/Get-Involved/Student-Organizations.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/engagement/student_organizations.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Get Involved > Student Government Association > > > |  | /Student-Life/Get-Involved/Student-Government-Association.cfm | Interior | Create Empty Page | Create | UBalt Outline
Dagemawit Kebede | SSSS | This page does not belong to SSSS. | Completed Edit |  | Student Life > Get Involved > Student Center > > > | ubalt.edu/campus-life/student_center | /Student-Life/Get-Involved/Student-Center/index.cfm | Interior | Migrate Merge | Merge | UBalt Outline | This should belong to Auxiliary Services. | ubalt.edu/campus-life/student_center | ubalt.edu/campus-life/student_center/index.cfm
Dagemawit Kebede | SSSS | This page does not belong to SSSS. | Completed Edit |  | Student Life > Get Involved > Student Center > > > | ubalt.edu/campus-life/student_center/art%20gallery.cfm | /Student-Life/Get-Involved/Student-Center/art-gallery.cfm | Interior | Migrate | Keep (Revise) | Migration-Ready | This should belong to Auxiliary Services. | ubalt.edu/campus-life/student_center/art%20gallery.cfm
Dagemawit Kebede | SSSS | This page does not belong to SSSS. | Completed Edit |  | Student Life > Get Involved > Student Center > > > | ubalt.edu/campus-life/student_center/game%20room.cfm | /Student-Life/Get-Involved/Student-Center/game-room.cfm | Interior | Migrate | Keep (Revise) | Migration-Ready | This should belong to OTS. | ubalt.edu/campus-life/student_center/game%20room.cfm
Dagemawit Kebede | SSSS | This page does not belong to SSSS. | Completed Edit |  | Student Life > Get Involved > Student Center > > > | ubalt.edu/campus-life/student_center/interfaith-room.cfm | /Student-Life/Get-Involved/Student-Center/interfaith-room.cfm | Interior | Migrate | Keep (Revise) | Migration-Ready | This should belong to Auxiliary Services. | ubalt.edu/campus-life/student_center/interfaith-room.cfm
Dagemawit Kebede | SSSS | This page does not belong to SSSS. | Completed Edit |  | Student Life > Get Involved > Student Center > > > | ubalt.edu/campus-life/student_center/sc-policies.cfm | /Student-Life/Get-Involved/Student-Center/sc-policies.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | This should belong to Auxiliary Services. | ubalt.edu/campus-life/student_center/sc-policies.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Get Involved > Inclusion Programs > > > |  | /Student-Life/Get-Involved/Inclusion-Programs.cfm | Interior | Create Empty Page | Create | UBalt Outline
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Get Involved > Volunteering & Service-Learning > > > | ubalt.edu/campus-life/engagement/be-more | /student-life/Get-Involved/Volunteering-and-Service-Learning/bee-engaged/index.cfm | Interior | Migrate | Keep (Revise) | Migration-Ready | change directory to "service". | ubalt.edu/campus-life/engagement/be-more | ubalt.edu/campus-life/engagement/be-more/index.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Get Involved > Volunteering & Service-Learning > > > | ubalt.edu/campus-life/engagement/be-more/alternative-breaks.cfm | /Student-Life/Get-Involved/Volunteering-and-Service-Learning/bee-engaged/alternative-breaks.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | change directory to "service". | ubalt.edu/campus-life/engagement/be-more/alternative-breaks.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Get Involved > Volunteering & Service-Learning > > > | ubalt.edu/campus-life/engagement/be-more/donate.cfm | /Student-Life/Get-Involved/Volunteering-and-Service-Learning/bee-engaged/donate.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | Move to Student Support/Pantry/Donate, not student life. Inputted work order. | ubalt.edu/campus-life/engagement/be-more/donate.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Get Involved > Volunteering & Service-Learning > > > | ubalt.edu/campus-life/engagement/be-more/pantry.cfm | /Student-Life/Get-Involved/Volunteering-and-Service-Learning/bee-engaged/pantry.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | Move to Student Support (/Student-Life/Student-Support/Campus-Pantry.cfm), not student life. Inputted work order. | ubalt.edu/campus-life/engagement/be-more/pantry.cfm
Dagemawit Kebede | SSSS | DELETE PAGE | Completed Edit |  | Student Life > Get Involved > Volunteering & Service-Learning > > > | ubalt.edu/campus-life/engagement/be-more/participate.cfm | /Student-Life/Get-Involved/Volunteering-and-Service-Learning/bee-engaged/participate.cfm | Interior | Migrate | DELETE | UBalt Outline | DELETE PAGE. | ubalt.edu/campus-life/engagement/be-more/participate.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Get Involved > Volunteering & Service-Learning > > > | ubalt.edu/campus-life/engagement/be-more/service-opportunities.cfm | /Student-Life/Get-Involved/Volunteering-and-Service-Learning/bee-engaged/service-opportunities.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | change directory to "service". | ubalt.edu/campus-life/engagement/be-more/service-opportunities.cfm
Dagemawit Kebede | SSSS | DELETE PAGE | Completed Edit |  | Student Life > Get Involved > Volunteering & Service-Learning > > > | ubalt.edu/campus-life/engagement/be-more/volunteer.cfm | /Student-Life/Get-Involved/Volunteering-and-Service-Learning/bee-engaged/volunteer.cfm | Interior | Migrate | DELETE | UBalt Outline | DELETE PAGE. | ubalt.edu/campus-life/engagement/be-more/volunteer.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/campus-life/disability-access-services | /Student-Life/Student-Support/Health-and-Wellness/disability-access-services.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | DM | ubalt.edu/campus-life/disability-access-services | ubalt.edu/campus-life/disability-access-services/index.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/campus-life/disability-access-services/contact-us.cfm | /Student-Life/Student-Support/Health-and-Wellness/contact-us.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | DM | ubalt.edu/campus-life/disability-access-services/contact-us.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center | /Student-Life/Student-Support/Career-and-Internship-Center/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/about-us | /Student-Life/Student-Support/Career-and-Internship-Center/about-us.cfm | Interior | Migrate | Keep (Revise) | Migration-Ready |  | ubalt.edu/campus-life/career-center/about-us
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/about-us/facts-and-figures.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/about-us/facts-and-figures.cfm | Interior | Migrate | Keep (Revise) | Migration-Ready |  | ubalt.edu/campus-life/career-center/about-us/facts-and-figures.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/about-us/index.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/about-us/index.cfm | Interior | Migrate | Keep (Revise) | Migration-Ready | duplicate | ubalt.edu/campus-life/career-center/about-us/index.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-closet-donate.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/career-closet-donate.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-closet-donate.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-closet.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/career-closet.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-closet.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-coaching.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/career-coaching.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-coaching.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online | /Student-Life/Student-Support/Career-and-Internship-Center/career-services-online.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/career-cycle | /Student-Life/Student-Support/Career-and-Internship-Center/career-cycle.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/career-cycle
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/communicate-your-brand.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/communicate-your-brand.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/communicate-your-brand.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/create-your-opportunities.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/create-your-opportunities.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/create-your-opportunities.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/discover-your-direction.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/discover-your-direction.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/discover-your-direction.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/explore-world-work.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/explore-world-work.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/explore-world-work.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/gain-experience.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/gain-experience.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/gain-experience.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/index.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | duplicate | ubalt.edu/campus-life/career-center/career-services-online/career-cycle/index.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/career-options-by-major.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/career-options-by-major.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | Use content for Major by career feature | ubalt.edu/campus-life/career-center/career-services-online/career-options-by-major.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguide2.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/creativecareersguide2.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguide2.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguidecreativewritingmfa.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/creativecareersguidecreativewritingmfa.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguidecreativewritingmfa.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguideenglishcreativewriting.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/creativecareersguideenglishcreativewriting.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguideenglishcreativewriting.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguideinformationinteractiondesign.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/creativecareersguideinformationinteractiondesign.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguideinformationinteractiondesign.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguideintegrated%20design.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/creativecareersguideintegrated-design.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguideintegrated%20design.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguideintegratedarts.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/creativecareersguideintegratedarts.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguideintegratedarts.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguideinteractiondesign.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/creativecareersguideinteractiondesign.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguideinteractiondesign.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguidesimulationandgamedesign.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/creativecareersguidesimulationandgamedesign.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/creativecareersguidesimulationandgamedesign.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides | /Student-Life/Student-Support/Career-and-Internship-Center/how-to-guides.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/find-job-internship.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/how-to-guides/find-job-internship.cfm | Interior | Migrate | Keep (Revise) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/find-job-internship.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/get-a-job-on-campus.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/how-to-guides/get-a-job-on-campus.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/get-a-job-on-campus.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/index.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/how-to-guides/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | duplicate | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/index.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/navigate-ubworks.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/how-to-guides/navigate-ubworks.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/navigate-ubworks.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/polish-your-resume.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/how-to-guides/polish-your-resume.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/polish-your-resume.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/prepare-for-interview.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/how-to-guides/prepare-for-interview.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/prepare-for-interview.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/sample-resumes.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/how-to-guides/sample-resumes.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/how-to-guides/sample-resumes.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/index.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/career-services-online/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | duplicate | ubalt.edu/campus-life/career-center/career-services-online/index.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/career-services-online/where-do-ub-graduates-work.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/career-services-online/where-do-ub-graduates-work.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/career-services-online/where-do-ub-graduates-work.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/events | /Student-Life/Student-Support/Career-and-Internship-Center/events.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/events
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/events/index.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/events/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | duplicate | ubalt.edu/campus-life/career-center/events/index.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/faculty-staff.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/faculty-staff.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/faculty-staff.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/index.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | duplicate | ubalt.edu/campus-life/career-center/index.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/strengthsquest/index.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/strengthsquest/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/strengthsquest/index.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/strengthsquest/classroom-presentations.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/strengthsquest/classroom-presentations.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/strengthsquest/classroom-presentations.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/strengthsquest/index.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/strengthsquest/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | duplicate | ubalt.edu/campus-life/career-center/strengthsquest/index.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/strengthsquest/strengths-faq.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/strengthsquest/strengths-faq.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/strengthsquest/strengths-faq.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/strengthsquest/student-coaching.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/strengthsquest/student-coaching.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/strengthsquest/student-coaching.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/strengthsquest/talent-themes.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/strengthsquest/talent-themes.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/strengthsquest/talent-themes.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Student Life > Student Support > Career & Internship Center > > > | ubalt.edu/campus-life/career-center/students-alumni.cfm | /Student-Life/Student-Support/Career-and-Internship-Center/career-center/students-alumni.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/career-center/students-alumni.cfm
Dagemawit Kebede | SSSS | Alicia Ryan | Completed Edit |  | Student Life > Student Support > Diversity & International Services > > > | ubalt.edu/campus-life/diversity-and-international-services | /Student-Life/Student-Support/Diversity-and-International-Services/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/diversity-and-international-services | ubalt.edu/campus-life/diversity-and-international-services//index.cfm | ubalt.edu/campus-life/diversity-and-international-services/index.cfm
Dagemawit Kebede | SSSS | Alicia Ryan | Completed Edit |  | Student Life > Student Support > Diversity & International Services > > > | ubalt.edu/campus-life/diversity-and-international-services/safe-space.cfm | /Student-Life/Student-Support/Diversity-and-International-Services/safe-space.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | Revisions in progress by DIS | ubalt.edu/campus-life/diversity-and-international-services/safe-space.cfm
Dagemawit Kebede | SSSS | Dena Allen-Few | 2nd Review Completed |  | Student Life > Student Support > Veteran Support > The Bob Parsons Veteran Center > Main > > | ubalt.edu/campus-life/veterans | /Student-Life/Student-Support/Veteran-Support/The-Bob-Parsons-Veteran-Center/index.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/veterans | ubalt.edu/campus-life/veterans/contact.cfm | ubalt.edu/campus-life/veterans/campus-life.cfm
Dagemawit Kebede | SSSS | Dena Allen-Few | Completed Edit |  | Student Life > Student Support > Veteran Support > The Bob Parsons Veteran Center > Resources > > | ubalt.edu/campus-life/veterans/resources.cfm | /Student-Life/Student-Support/Veteran-Support/The-Bob-Parsons-Veteran-Center/Resources.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/veterans/resources.cfm
Dagemawit Kebede | SSSS | Dena Allen-Few | Completed Edit |  | Student Life > Student Support > Veteran Support > The Bob Parsons Veteran Center > ROTC > > | ubalt.edu/campus-life/veterans/rotc-at-ub.cfm | /Student-Life/Student-Support/Veteran-Support/The-Bob-Parsons-Veteran-Center/ROTC.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/veterans/rotc-at-ub.cfm
Dagemawit Kebede | SSSS | DELETE PAGE - MOVED FROM STUDENT LIFE AND IT WILL LIVE IN STUDENT SUPPORT | Completed Edit |  | Student Life > Student Support > Campus Pantry > > > |  | /Student-Life/Student-Support/Campus-Pantry.cfm | Interior | Create Empty Page | DELETE | UBalt Outline | DELETE, SEE 15 ABOVE
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/campus-life/disability-access-services/online_learning_accessibility_resources.cfm | /Student-Life/Student-Support/Health-and-Wellness/online_learning_accessibility_resources.cfm | Interior | Migrate | Delete | UBalt Outline | DM | ubalt.edu/campus-life/disability-access-services/online_learning_accessibility_resources.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/campus-life/disability-access-services/students | /Student-Life/Student-Support/Health-and-Wellness/students/index.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | DM | ubalt.edu/campus-life/disability-access-services/students | ubalt.edu/campus-life/disability-access-services/students/index.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/campus-life/disability-access-services/students/documentation-guidelines.cfm | /Student-Life/Student-Support/Health-and-Wellness/students/documentation-guidelines.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | DM | ubalt.edu/campus-life/disability-access-services/students/documentation-guidelines.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/campus-life/disability-access-services/students/faqs.cfm | /Student-Life/Student-Support/Health-and-Wellness/students/faqs.cfm | Interior | Migrate | Delete | UBalt Outline | DM | ubalt.edu/campus-life/disability-access-services/students/faqs.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/campus-life/disability-access-services/students/forms.cfm | /Student-Life/Student-Support/Health-and-Wellness/students/forms.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline | DM | ubalt.edu/campus-life/disability-access-services/students/forms.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/campus-life/disability-access-services/students/scholarships.cfm | /Student-Life/Student-Support/Health-and-Wellness/students/scholarships.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | DM | ubalt.edu/campus-life/disability-access-services/students/scholarships.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/campus-life/disability-access-services/support-services.cfm | /Student-Life/Student-Support/Health-and-Wellness/support-services.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | DM | ubalt.edu/campus-life/disability-access-services/support-services.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/campus-life/disability-access-services/useful-links.cfm | /Student-Life/Student-Support/Health-and-Wellness/useful-links.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | DM | ubalt.edu/campus-life/disability-access-services/useful-links.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Information Library > Academic Support and Resources > Faculty Resources > Disability Access Services | ubalt.edu/campus-life/disability-access-services/faculty | /myubalt/Information-Library/Academic-Support-and-Resources/Faculty-Resources/Disability-Access-Services/faculty.cfm | Intranet | Migrate | Keep (Revise) | Migration-Ready | DM | ubalt.edu/campus-life/disability-access-services/faculty
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Information Library > Academic Support and Resources > Faculty Resources > Disability Access Services | ubalt.edu/campus-life/disability-access-services/faculty/index.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Faculty-Resources/Disability-Access-Services/index.cfm | Intranet | Migrate | Keep (Revise) | Migration-Ready | We had acess issue. Ticket has been submited to Market for acess request to this page. | ubalt.edu/campus-life/disability-access-services/faculty/index.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Information Library > Academic Support and Resources > Faculty Resources > Disability Access Services > Accessibility Tips | ubalt.edu/campus-life/disability-access-services/faculty/accessibility-tips.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Faculty-Resources/Disability-Access-Services/Accessibility-Tips.cfm | Intranet | Migrate | Keep (Revise) | Migration-Ready | DM | ubalt.edu/campus-life/disability-access-services/faculty/accessibility-tips.cfm
Dagemawit Kebede | SSSS | Karyn Schulz / María Maclay | 2nd Review Completed |  | Information Library > Academic Support and Resources > Faculty Resources > Disability Access Services > Supervised Testing | ubalt.edu/campus-life/disability-access-services/faculty/supervised-testing.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Faculty-Resources/Disability-Access-Services/Supervised-Testing.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | DM | ubalt.edu/campus-life/disability-access-services/faculty/supervised-testing.cfm
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | Footer > COVID-19 | ubalt.edu/covid-19 | /Footer/COVID-19/index.cfm |  | Migrate | Keep (Revise) | Migration-Ready | Revisions in progress | ubalt.edu/covid-19
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | Footer > COVID-19 > Positive Test Responsibilities | ubalt.edu/covid-19/positive-test-responsibilities.cfm | /Footer/COVID-19/Positive-Test-Responsibilities.cfm |  | Migrate | Keep (Revise) | Migration-Ready | Revisions in progress | ubalt.edu/covid-19/positive-test-responsibilities.cfm
Dagemawit Kebede | SSSS | DELETE PAGE | Completed Edit |  | Student Life > Campus Resources > Main > > > |  | /Student-Life/Campus-Resources/index.cfm | Interior | Create Empty Page | Create | UBalt Outline |  |  |  | ubalt.edu/about-ub/offices-and-services/auxiliary/food-services/vending.cfm
Dagemawit Kebede | SSSS | DELETE PAGE | Completed Edit |  | Student Life > Campus Resources > Building Hours > > > |  | /Student-Life/Campus-Resources/Building-Hours.cfm | Interior | Create Empty Page | Create | UBalt Outline | This should live with Aux Services/Facilities.
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | Footer > COVID-19 > For Faculty | ubalt.edu/covid-19/for-faculty.cfm | /Footer/COVID-19/For-Faculty.cfm |  | Migrate | Keep (Revise) | Migration-Ready | Revisions in progress | ubalt.edu/covid-19/for-faculty.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Main > > > |  | /Student-Life/Campus-Traditions/index.cfm | Interior | Create Empty Page | Create | UBalt Outline
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement | /Student-Life/Campus-Traditions/Commencement/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/engagement/commencement | ubalt.edu/campus-life/engagement/commencement/index.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | About > Centers, Clinics, & Institutes > Rosenberg Center for Student Engagement and Inclusion > > > | ubalt.edu/campus-life/engagement | /About/Centers-Clinics-and-Institutes/Rosenberg-Center-for-Student-Engagement-and-Inclusion/index.cfm | Interior | Migrate | Move/Create | Migration-Ready | Move to under Student Life- Get Involved. Put in work order. | ubalt.edu/campus-life/engagement
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/accommodations%20and%20commencement%20invitation%20letters.cfm | /Student-Life/Campus-Traditions/Commencement/accommodations-and-commencement-invitation-letters.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/accommodations%20and%20commencement%20invitation%20letters.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/commencement%20tickets.cfm | /Student-Life/Campus-Traditions/Commencement/commencement-tickets.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/commencement%20tickets.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/contact.cfm | /Student-Life/Campus-Traditions/Commencement/contact.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/contact.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/day%20of%20guest%20instructions.cfm | /Student-Life/Campus-Traditions/Commencement/day-of-guest-instructions.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/day%20of%20guest%20instructions.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/grad%20fest.cfm | /Student-Life/Campus-Traditions/Commencement/grad-fest.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/grad%20fest.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/graduation_faqs.cfm | /Student-Life/Campus-Traditions/Commencement/graduation_faqs.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/graduation_faqs.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/graduation%20applications%20and%20eligibility%20.cfm | /Student-Life/Campus-Traditions/Commencement/graduation-applications-and-eligibility-.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/graduation%20applications%20and%20eligibility%20.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/graduation%20regalia.cfm | /Student-Life/Campus-Traditions/Commencement/graduation-regalia.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/graduation%20regalia.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/honors%20and%20military%20recognition.cfm | /Student-Life/Campus-Traditions/Commencement/honors-and-military-recognition.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/honors%20and%20military%20recognition.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/information%20for%20degree%20candidates.cfm | /Student-Life/Campus-Traditions/Commencement/information-for-degree-candidates.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/information%20for%20degree%20candidates.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/instructions%20for%20families%20and%20guests.cfm | /Student-Life/Campus-Traditions/Commencement/instructions-for-families-and-guests.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/instructions%20for%20families%20and%20guests.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/photos%20and%20flowers.cfm | /Student-Life/Campus-Traditions/Commencement/photos-and-flowers.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/photos%20and%20flowers.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Commencement > > > | ubalt.edu/campus-life/engagement/commencement/student%20speaker%20applications.cfm | /Student-Life/Campus-Traditions/Commencement/student-speaker-applications.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/commencement/student%20speaker%20applications.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Orientation > > > | ubalt.edu/campus-life/engagement/orientation | /Student-Life/Campus-Traditions/Orientation/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/engagement/orientation | ubalt.edu/campus-life/engagement/orientation/index.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Orientation > > > | ubalt.edu/campus-life/engagement/orientation/freshman%20steps%20for%20success%20at%20ub.cfm | /Student-Life/Campus-Traditions/Orientation/freshman-steps-for-success-at-ub.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/orientation/freshman%20steps%20for%20success%20at%20ub.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Orientation > > > | ubalt.edu/campus-life/engagement/orientation/graduate%20steps%20for%20success%20at%20ub.cfm | /Student-Life/Campus-Traditions/Orientation/graduate-steps-for-success-at-ub.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/orientation/graduate%20steps%20for%20success%20at%20ub.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Orientation > > > | ubalt.edu/campus-life/engagement/orientation/orientation%20faqs.cfm | /Student-Life/Campus-Traditions/Orientation/orientation-faqs.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/orientation/orientation%20faqs.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Orientation > > > | ubalt.edu/campus-life/engagement/orientation/parent-family-info.cfm | /Student-Life/Campus-Traditions/Orientation/parent-family-info.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/orientation/parent-family-info.cfm
Dagemawit Kebede | SSSS | DELETE PAGE | Completed Edit |  | Student Life > Campus Traditions > Orientation > > > | ubalt.edu/campus-life/engagement/orientation/parents%20and%20family%20members.cfm | /Student-Life/Campus-Traditions/Orientation/parents-and-family-members.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/orientation/parents%20and%20family%20members.cfm
Dagemawit Kebede | SSSS | DELETE PAGE | Completed Edit |  | Student Life > Campus Traditions > Orientation > > > | ubalt.edu/campus-life/engagement/orientation/transfer%20orientation.cfm | /Student-Life/Campus-Traditions/Orientation/transfer-orientation.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/orientation/transfer%20orientation.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Orientation > > > | ubalt.edu/campus-life/engagement/orientation/transfer%20steps%20for%20success%20at%20ub.cfm | /Student-Life/Campus-Traditions/Orientation/transfer-steps-for-success-at-ub.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/orientation/transfer%20steps%20for%20success%20at%20ub.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Orientation > > > | ubalt.edu/campus-life/engagement/orientation/what%20is%20orientation.cfm | /Student-Life/Campus-Traditions/Orientation/what-is-orientation.cfm | Interior | Migrate | Keep (As Is) | UBalt Outline |  | ubalt.edu/campus-life/engagement/orientation/what%20is%20orientation.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Welcome Week > > > | ubalt.edu/campus-life/engagement/welcome-weeks.cfm | /Student-Life/Campus-Traditions/Welcome-Week.cfm | Interior | Migrate | Keep (Revise) | Migration-Ready | Edit to be ubalt.edu/campus-life/engagement/welcome-week.cfm (take off s since only 1 week) | ubalt.edu/campus-life/engagement/welcome-weeks.cfm
Dagemawit Kebede | SSSS | This page does not belong to SSSS ( Marketing) | Completed Edit |  | Student Life > Campus Traditions > Eubie the Bee > > > | ubalt.edu/campus-life/the-ub-bee | /Student-Life/Campus-Traditions/Eubie-the-Bee.cfm | Interior | Migrate Merge | Merge | UBalt Outline | This should belong to Marketing. EW: Merge with landing page ubalt.edu/campus-life/the-ub-bee/index.cfm | ubalt.edu/campus-life/the-ub-bee | ubalt.edu/campus-life/the-ub-bee/index.cfm | ubalt.edu/campus-life/the-ub-bee/ub-bee-history-.cfm
Dagemawit Kebede | SSSS | Eric White | Marketing |  | Student Life > Events Calendar > Main > > > | ubalt.edu/calendar/calendar.cfm | /Student-Life/Events-Calendar/index.cfm | OU Calendar lIst | Create Empty Page | Keep (Revise) | Migration-Ready | MIgrate to new CMS Calendar Module | ubalt.edu/calendar/calendar.cfm
Dagemawit Kebede | SSSS | Eric White | Marketing |  | Student Life > Events Calendar > [Event Detail Page] > > > |  | /Student-Life/Events-Calendar/[Event-Detail-Page].cfm | OU Calendar Event Detail | Create Empty Page | Keep (As Is) | Migration-Ready
Dagemawit Kebede | SSSS | Alicia Ryan | Completed Edit |  | About > Diversity & Inclusion > > > > | ubalt.edu/campus-life/engagement/inclusion | /About/Diversity-and-Inclusion/inclusion/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/engagement/inclusion | ubalt.edu/campus-life/engagement/inclusion/index.cfm
Dagemawit Kebede | SSSS | Alicia Ryan | Completed Edit |  | About > Diversity & Inclusion > > > > | ubalt.edu/campus-life/engagement/inclusion/pride.cfm | /About/Diversity-and-Inclusion/inclusion/pride.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/engagement/inclusion/pride.cfm
Dagemawit Kebede | SSSS | Alicia Ryan | Completed Edit |  | About > Diversity & Inclusion > > > > | ubalt.edu/campus-life/engagement/inclusion/resources-aapi.cfm | /About/Diversity-and-Inclusion/inclusion/resources-aapi.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/engagement/inclusion/resources-aapi.cfm
Dagemawit Kebede | SSSS | Alicia Ryan | Completed Edit |  | About > Diversity & Inclusion > > > > | ubalt.edu/campus-life/engagement/inclusion/resources-african-american.cfm | /About/Diversity-and-Inclusion/inclusion/resources-african-american.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/engagement/inclusion/resources-african-american.cfm
Dagemawit Kebede | SSSS | Alicia Ryan | Completed Edit |  | About > Diversity & Inclusion > > > > | ubalt.edu/campus-life/engagement/inclusion/resources-indigenous.cfm | /About/Diversity-and-Inclusion/inclusion/resources-indigenous.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/engagement/inclusion/resources-indigenous.cfm
Dagemawit Kebede | SSSS | Alicia Ryan | Completed Edit |  | About > Diversity & Inclusion > > > > | ubalt.edu/campus-life/engagement/inclusion/resources-latinx.cfm | /About/Diversity-and-Inclusion/inclusion/resources-latinx.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/engagement/inclusion/resources-latinx.cfm
Dagemawit Kebede | SSSS | Alicia Ryan | Completed Edit |  | About > Diversity & Inclusion > > > > | ubalt.edu/campus-life/engagement/inclusion/resources-lgbtqia.cfm | /About/Diversity-and-Inclusion/inclusion/resources-lgbtqia.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/engagement/inclusion/resources-lgbtqia.cfm
Dagemawit Kebede | SSSS | Alicia Ryan | Completed Edit |  | About > Diversity & Inclusion > > > > | ubalt.edu/campus-life/engagement/inclusion/resources-women.cfm | /About/Diversity-and-Inclusion/inclusion/resources-women.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/engagement/inclusion/resources-women.cfm
Dagemawit Kebede | SSSS | DELETE PAGE | Completed Edit |  | About > Diversity & Inclusion > > > > | ubalt.edu/campus-life/engagement/inclusion/wild.cfm | /About/Diversity-and-Inclusion/inclusion/wild.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | WILD is an old event, delete page recommendation or make it unviewable. | ubalt.edu/campus-life/engagement/inclusion/wild.cfm
Dagemawit Kebede | SSSS | Dagemawit Kebede | Completed Edit |  | About > Offices & Services > Student Success & Support Services > > > | ubalt.edu/about-ub/offices-and-services/avpforsa | /About/Offices-and-Services/Student-Success-and-Support-Services/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | Need to update links | ubalt.edu/about-ub/offices-and-services/avpforsa
Dagemawit Kebede | SSSS | Dagemawit Kebede | Completed Edit |  | About > Offices & Services > Student Success & Support Services > > > | ubalt.edu/about-ub/offices-and-services/avpforsa/about-student-affairs.cfm | /About/Offices-and-Services/Student-Success-and-Support-Services/about-student-affairs.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | Need to update links | ubalt.edu/about-ub/offices-and-services/avpforsa/about-student-affairs.cfm
Dagemawit Kebede | SSSS | Dagemawit Kebede This page can be Archived | Completed Edit | Phase 2 | About > Offices & Services > Student Success & Support Services > > > | ubalt.edu/about-ub/offices-and-services/avpforsa/beyou | /About/Offices-and-Services/Student-Success-and-Support-Services/beyou.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | Need to update links | ubalt.edu/about-ub/offices-and-services/avpforsa/beyou
Dagemawit Kebede | SSSS | Dagemawit Kebede | Completed Edit |  | About > Offices & Services > Student Success & Support Services > > > | ubalt.edu/about-ub/offices-and-services/avpforsa/index.cfm | /About/Offices-and-Services/Student-Success-and-Support-Services/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | Need to update links | ubalt.edu/about-ub/offices-and-services/avpforsa/index.cfm
Dagemawit Kebede | SSSS | Dagemawit Kebede | Completed Edit |  | About > Offices & Services > Student Success & Support Services > > > | ubalt.edu/about-ub/offices-and-services/avpforsa/meet-our-staff.cfm | /About/Offices-and-Services/Student-Success-and-Support-Services/meet-our-staff.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | Need to update links | ubalt.edu/about-ub/offices-and-services/avpforsa/meet-our-staff.cfm
Dagemawit Kebede | SSSS | Dagemawit Kebede | Completed Edit |  | About > Offices & Services > Student Success & Support Services > > > | ubalt.edu/about-ub/offices-and-services/avpforsa/programsandinitiatives.cfm | /About/Offices-and-Services/Student-Success-and-Support-Services/programsandinitiatives.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | EW: Propose adding discription/contect to listed links - DONE and need to update links | ubalt.edu/about-ub/offices-and-services/avpforsa/programsandinitiatives.cfm
Dagemawit Kebede | SSSS | Dagemawit Kebede | Completed Edit |  | About > Offices & Services > Student Success & Support Services > > > | ubalt.edu/about-ub/offices-and-services/avpforsa/resourcesandlinks.cfm | /About/Offices-and-Services/Student-Success-and-Support-Services/resourcesandlinks.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | Need to update links | ubalt.edu/about-ub/offices-and-services/avpforsa/resourcesandlinks.cfm
Dagemawit Kebede | SSSS | Dagemawit Kebede- THIS PAGE CAN BE DELETED | Completed Edit |  | About > Offices & Services > Student Success & Support Services > > > | ubalt.edu/about-ub/offices-and-services/avpforsa/scholarly-practitioners.cfm | /About/Offices-and-Services/Student-Success-and-Support-Services/scholarly-practitioners.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | Need to update links | ubalt.edu/about-ub/offices-and-services/avpforsa/scholarly-practitioners.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | Student Life > Student Support > Academic Support > > > | ubalt.edu/academics/academic-support | /Student-Life/Student-Support/Academic-Support/academic-support.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | Student Life > Student Support > Student Assistance Program > > > |  | /Student-Life/Student-Support/Student-Assistance-Program.cfm | Interior | Create Empty Page | Create | UBalt Outline |  |  | Duplicate page - Please replace with the following page destination /about/offices-and-services/dean-of-students/sap/index.pcf
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | Student Life > Student Support > Health & Wellness > > > |  | /Student-Life/Student-Support/Health-and-Wellness/index.cfm | Interior | Create Empty Page | Create | UBalt Outline
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/mpx.cfm | /Student-Life/Student-Support/Health-and-Wellness/mpx.cfm | Interior | Migrate | Keep (Revise) | UBalt Outline | To be moved to heaalth portion of the website as devleoped | ubalt.edu/about-ub/offices-and-services/dean-of-students/mpx.cfm
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | Student Life > Student Support > Health & Wellness > > > | ubalt.edu/campus-life/counseling-services | /Student-Life/Student-Support/Health-and-Wellness/counseling-services.cfm | Interior | Migrate Merge | Merge | UBalt Outline | DM: Dupe w/ /index? | ubalt.edu/campus-life/counseling-services | ubalt.edu/campus-life/counseling-services/index.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students | /About/Offices-and-Services/Dean-of-Students/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students | SAP link at bottom of page is to duplicated SAP page in Student Life Destination. This needs to be replaced with the page from the following destination - /about/offices-and-services/dean-of-students/sap/index.pcf | Addtionally, this page is not linked from the Homepage Menu drop down from Student Life - Cannot update it to this destination
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/best | /About/Offices-and-Services/Dean-of-Students/best/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/best | Page is unsearchable on refreshed environment
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/best/additional%20support%20and%20resources.cfm | /About/Offices-and-Services/Dean-of-Students/best/additional-support-and-resources.cfm/additional-support-and-resources.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/best/additional%20support%20and%20resources.cfm | Link to SAP page is to the duplicate Student Life page and not the page located at /about/offices-and-services/dean-of-students/sap/index.pcf
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/best/bias%20experience%20support%20team%20members.cfm | /About/Offices-and-Services/Dean-of-Students/best/bias-experience-support-team-members.cfm/bias-experience-support-team-members.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/best/bias%20experience%20support%20team%20members.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/best/frequently%20asked%20questions.cfm | /About/Offices-and-Services/Dean-of-Students/frequently-asked-questions.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/best/frequently%20asked%20questions.cfm | This page needs to be relocated to the following destination folder to be able to link to Section Menu for BEST team home page -> /About/Offices-and-Services/Dean-of-Students/best/
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/best/reporting%20a%20bias%20experience.cfm | /About/Offices-and-Services/Dean-of-Students/reporting-a-bias-experience.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/best/reporting%20a%20bias%20experience.cfm | This page needs to be relocated to the following destination to be able to link to Section Menu for BEST team -> /About/Offices-and-Services/Dean-of-Students/best/
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/best/responding%20to%20bias%20experience%20reports.cfm | /About/Offices-and-Services/Dean-of-Students/responding-to-bias-experience-reports.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/best/responding%20to%20bias%20experience%20reports.cfm | This page needs to be relocated to the following destination to be able to link to Section Menu for BEST team -> /About/Offices-and-Services/Dean-of-Students/best/
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards | /About/Offices-and-Services/Dean-of-Students/community-standards.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards/board%20hearing%20panelists.cfm | /About/Offices-and-Services/Dean-of-Students/board-hearing-panelists.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards/board%20hearing%20panelists.cfm
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards/forms/index.cfm | /About/Offices-and-Services/Dean-of-Students/community-standards/forms/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards/forms/index.cfm
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards/index.cfm | /About/Offices-and-Services/Dean-of-Students/community-standards/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards/index.cfm
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards/student%20conduct%20records%20checks.cfm | /About/Offices-and-Services/Dean-of-Students/community-standards/student-conduct-records-checks.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards/student%20conduct%20records%20checks.cfm
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards/trained%20support%20individual.cfm | /About/Offices-and-Services/Dean-of-Students/community-standards/trained-support-individual.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/community-standards/trained%20support%20individual.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/community%20reporting%20portal.cfm | /About/Offices-and-Services/Dean-of-Students/community-reporting-portal.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/community%20reporting%20portal.cfm | SAP link goes to dead page - Needs to link to this page located at --> /About/Offices-and-Services/Dean-of-Students/sap/index.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass | /About/Offices-and-Services/Dean-of-Students/compass.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass | Confidentiality and Privacy drop down links to Dead FERPA page - we do not control that page to update the link
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/alcohol%20and%20drug%20services.cfm | /About/Offices-and-Services/Dean-of-Students/alcohol-and-drug-services.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/alcohol%20and%20drug%20services.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/buzz%20folder.cfm | /About/Offices-and-Services/Dean-of-Students/buzz-folder.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/buzz%20folder.cfm | Active ticket to redesign page content to better fit new layout
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/care%20team.cfm | /About/Offices-and-Services/Dean-of-Students/care-team.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/care%20team.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/external%20resources%20for%20students.cfm | /About/Offices-and-Services/Dean-of-Students/external-resources-for-students.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/external%20resources%20for%20students.cfm
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/health%20insurance%20information.cfm | /About/Offices-and-Services/Dean-of-Students/health-insurance-information.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/health%20insurance%20information.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/index.cfm | /About/Offices-and-Services/Dean-of-Students/compass/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/index.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/mental%20health%20ally%20award.cfm | /About/Offices-and-Services/Dean-of-Students/compass/mental-health-ally-award.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/mental%20health%20ally%20award.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/mental%20health%20first%20aid.cfm | /About/Offices-and-Services/Dean-of-Students/compass/mental-health-first-aid.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/mental%20health%20first%20aid.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/resources%20for%20students.cfm | /About/Offices-and-Services/Dean-of-Students/compass/resources-for-students.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/resources%20for%20students.cfm | Following links are currently broken - Name Change Process, Sex Discrimination Policy, Student Conduct Forms, Student Handbook
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/umatter.cfm | /About/Offices-and-Services/Dean-of-Students/compass/umatter.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/compass/umatter.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/index.cfm | /About/Offices-and-Services/Dean-of-Students/index | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/index.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/meet%20the%20team.cfm | /About/Offices-and-Services/Dean-of-Students/meet-the-team.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/meet%20the%20team.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/mental%20health%20awareness%20and%20crisis%20prevention%20education.cfm | /About/Offices-and-Services/Dean-of-Students/mental-health-awareness-and-crisis-prevention-education.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/mental%20health%20awareness%20and%20crisis%20prevention%20education.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/resources.cfm | /About/Offices-and-Services/Dean-of-Students/resources.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/resources.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/resources%20for%20faculty%20and%20staff.cfm | /About/Offices-and-Services/Dean-of-Students/resources-for-faculty-and-staff.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/resources%20for%20faculty%20and%20staff.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/resources%20for%20pregnant%20students.cfm | /About/Offices-and-Services/Dean-of-Students/resources-for-pregnant-students.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/resources%20for%20pregnant%20students.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/resources%20for%20students.cfm | /About/Offices-and-Services/Dean-of-Students/resources-for-students.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/resources%20for%20students.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap | /About/Offices-and-Services/Dean-of-Students/sap.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/childcare%20referral%20services.cfm | /About/Offices-and-Services/Dean-of-Students/sap/childcare-referral-services.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/childcare%20referral%20services.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/eldercare%20referral%20services.cfm | /About/Offices-and-Services/Dean-of-Students/sap/eldercare-referral-services.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/eldercare%20referral%20services.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/financial%20consultation%20services.cfm | /About/Offices-and-Services/Dean-of-Students/sap/financial-consultation-services.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/financial%20consultation%20services.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/frequently%20asked%20questions.cfm | /About/Offices-and-Services/Dean-of-Students/sap/frequently-asked-questions.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/frequently%20asked%20questions.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/index.cfm | /About/Offices-and-Services/Dean-of-Students/sap/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/index.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/legal%20consultation%20services.cfm | /About/Offices-and-Services/Dean-of-Students/sap/legal-consultation-services.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/legal%20consultation%20services.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/sap%20testimonials.cfm | /About/Offices-and-Services/Dean-of-Students/sap/sap-testimonials.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/sap%20testimonials.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/video%20counsleing%20services.cfm | /About/Offices-and-Services/Dean-of-Students/sap/video-counsleing-services.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/video%20counsleing%20services.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/what%20happens.cfm | /About/Offices-and-Services/Dean-of-Students/sap/what-happens.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/sap/what%20happens.cfm
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/sexual%20assault%20prevention%20for%20adult%20learners%20tutorial%20faq.cfm | /About/Offices-and-Services/Dean-of-Students/sexual-assault-prevention-for-adult-learners-tutorial-faq.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/sexual%20assault%20prevention%20for%20adult%20learners%20tutorial%20faq.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | Student Life > Campus Traditions > Rock the Block > > > |  | /Student-Life/Campus-Traditions/Rocky-the-Block.cfm | Interior | Create Empty Page | Move/Create | UBalt Outline | PLEASE MOVE TO STUDENT LIFE DESTINATION (not about/centers), Liz put in a ticket
Dagemawit Kebede | SSSS | Anthony Butler | Completed Edit |  | About > Centers, Clinics, & Institutes > Rosenberg Center for Student Engagement and Inclusion > About Us > > | ubalt.edu/campus-life/engagement/about-us.cfm | /About/Centers-Clinics-and-Institutes/Rosenberg-Center-for-Student-Engagement-and-Inclusion/About-Us.cfm | Interior | Migrate | Move/Create | Migration-Ready | PLEASE MOVE TO STUDENT LIFE DESTINATION (not about/centers), Liz put in a ticket | ubalt.edu/campus-life/engagement/about-us.cfm
Dagemawit Kebede | SSSS | Elizabeth Purswani | Completed Edit |  | About > Centers, Clinics, & Institutes > Rosenberg Center for Student Engagement and Inclusion > Eubie Awards > > | ubalt.edu/campus-life/engagement/eubie_awards.cfm | /About/Centers-Clinics-and-Institutes/Rosenberg-Center-for-Student-Engagement-and-Inclusion/Eubie-Awards.cfm | Interior | Migrate | Move/Create | Migration-Ready | PLEASE MOVE TO Campus Traditions, Liz put in a ticket (Campus Traditions/Eubie Awards) | ubalt.edu/campus-life/engagement/eubie_awards.cfm
Dagemawit Kebede | SSSS | Anthony Butler | Completed Edit |  | About > Centers, Clinics, & Institutes > Rosenberg Center for Student Engagement and Inclusion > Vote > > | ubalt.edu/campus-life/engagement/vote | /About/Centers-Clinics-and-Institutes/Rosenberg-Center-for-Student-Engagement-and-Inclusion/Vote/index.cfm | Interior | Migrate | Move/Create | Migration-Ready | PLEASE MOVE TO STUDENT LIFE DESTINATION (not about/centers), Liz put in a ticket | ubalt.edu/campus-life/engagement/vote | ubalt.edu/campus-life/engagement/vote/index.cfm
Dagemawit Kebede | SSSS | Anthony Butler | Completed Edit |  | About > Centers, Clinics, & Institutes > Rosenberg Center for Student Engagement and Inclusion > Vote > > | ubalt.edu/campus-life/engagement/vote/beyond-voting.cfm | /About/Centers-Clinics-and-Institutes/Rosenberg-Center-for-Student-Engagement-and-Inclusion/Vote/beyond-voting.cfm | Interior | Migrate | Move/Create | Migration-Ready | PLEASE MOVE TO STUDENT LIFE DESTINATION (not about/centers), Liz put in a ticket | ubalt.edu/campus-life/engagement/vote/beyond-voting.cfm
Dagemawit Kebede | SSSS | Anthony Butler | Completed Edit |  | About > Centers, Clinics, & Institutes > Rosenberg Center for Student Engagement and Inclusion > Vote > > | ubalt.edu/campus-life/engagement/vote/events.cfm | /About/Centers-Clinics-and-Institutes/Rosenberg-Center-for-Student-Engagement-and-Inclusion/Vote/events.cfm | Interior | Migrate | Move/Create | Migration-Ready | PLEASE MOVE TO STUDENT LIFE DESTINATION (not about/centers), Liz put in a ticket | ubalt.edu/campus-life/engagement/vote/events.cfm
Dagemawit Kebede | SSSS | Anthony Butler | Completed Edit |  | About > Centers, Clinics, & Institutes > Rosenberg Center for Student Engagement and Inclusion > Vote > > | ubalt.edu/campus-life/engagement/vote/resources.cfm | /About/Centers-Clinics-and-Institutes/Rosenberg-Center-for-Student-Engagement-and-Inclusion/Vote/resources.cfm | Interior | Migrate | Move/Create | Migration-Ready | PLEASE MOVE TO STUDENT LIFE, Liz put in a ticket | ubalt.edu/campus-life/engagement/vote/resources.cfm
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Information For > Business Leaders & Employers > Main > > > > | ubalt.edu/campus-life/career-center/employers.cfm | Information-For/Business-Leaders-and-Employers/index.cfm | Interior | Migrate Merge | Merge | UBalt Outline | Cannot access page | ubalt.edu/campus-life/career-center/employers.cfm | ubalt.edu/merrick/about-the-school/faq.cfm
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Advising |  | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Advising.cfm | Intranet | Create Empty Page | Create | UBalt Outline
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Information Library > Academic Support and Resources > Academic Support > Career Services |  | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Career-Services.cfm | Intranet | Create Empty Page | Create | UBalt Outline | Cannot access page
Dagemawit Kebede | SSSS | This page does not belong to SSSS. | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Placement | ubalt.edu/academics/academic-support/placement | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Placement/placement.cfm | Intranet | Migrate | Keep (Revise) | Migration-Ready | Migrate dates to CMS Calendar Module | ubalt.edu/academics/academic-support/placement
Dagemawit Kebede | SSSS | This page does not belong to SSSS. | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Placement | ubalt.edu/academics/academic-support/placement/ | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Placement/.cfm | Intranet | Migrate | Keep (Revise) | Migration-Ready | Migrate dates to CMS Calendar Module | ubalt.edu/academics/academic-support/placement/.
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support | ubalt.edu/academics/academic-support/index.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/index.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/index.cfm
Dagemawit Kebede | SSSS | This page does not belong to SSSS. | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Placement | ubalt.edu/academics/academic-support/placement/index.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Placement/index.cfm | Intranet | Migrate | Keep (Revise) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/placement/index.cfm
Dagemawit Kebede | SSSS | Delete this page | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Undergraduate Support > Common Hour | ubalt.edu/academics/undergraduate/common-hour | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Undergraduate-Support/Common-Hour/common-hour.cfm | Intranet | Migrate | Keep (Revise) | Migration-Ready | Merge all into one page one Common Hour page the intranet | ubalt.edu/academics/undergraduate/common-hour
Dagemawit Kebede | SSSS | Lana Farley | 2nd Review Completed |  | Information Library > Academic Support and Resources > Academic Support > Career Services > CIC Videos | ubalt.edu/campus-life/career-center/career-services-online/cicvideosx.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Career-Services/CIC-Videos.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Cannot access page | ubalt.edu/campus-life/career-center/career-services-online/cicvideosx.cfm
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Undergraduate Support > First-Time Undergraduate Advising | ubalt.edu/academics/academic-support/freshman-advising | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Undergraduate-Support/First-Time-Undergraduate-Advising/freshman-advising.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/freshman-advising
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Undergraduate Support > First-Time Undergraduate Advising | ubalt.edu/academics/academic-support/freshman-advising/index.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Undergraduate-Support/First-Time-Undergraduate-Advising/index.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/freshman-advising/index.cfm
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Undergraduate Support > First-Time Undergraduate Advising > Contact Us | ubalt.edu/academics/academic-support/freshman-advising/contact-us.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Undergraduate-Support/First-Time-Undergraduate-Advising/Contact-Us.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/freshman-advising/contact-us.cfm
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Undergraduate Support > First-Time Undergraduate Advising > Early Alert | ubalt.edu/academics/academic-support/freshman-advising/early-alert.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Undergraduate-Support/First-Time-Undergraduate-Advising/Early-Alert.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/freshman-advising/early-alert.cfm
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Undergraduate Support > First-Time Undergraduate Advising > FAQs | ubalt.edu/academics/academic-support/freshman-advising/faqs.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Undergraduate-Support/First-Time-Undergraduate-Advising/FAQs.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/freshman-advising/faqs.cfm
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Undergraduate Support > First-Time Undergraduate Advising > Glossary | ubalt.edu/academics/academic-support/freshman-advising/glossary.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Undergraduate-Support/First-Time-Undergraduate-Advising/Glossary.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/freshman-advising/glossary.cfm
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Undergraduate Support > First-Time Undergraduate Advising > GPA Calculator | ubalt.edu/academics/academic-support/freshman-advising/gpa-calculator.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Undergraduate-Support/First-Time-Undergraduate-Advising/GPA-Calculator.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/freshman-advising/gpa-calculator.cfm
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Undergraduate Support > First-Time Undergraduate Advising > Parents and Families | ubalt.edu/academics/academic-support/freshman-advising/parents-and-families.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Undergraduate-Support/First-Time-Undergraduate-Advising/Parents-and-Families.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/freshman-advising/parents-and-families.cfm
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Undergraduate Support > First-Time Undergraduate Advising > Resources | ubalt.edu/academics/academic-support/freshman-advising/resources.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Undergraduate-Support/First-Time-Undergraduate-Advising/Resources.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/freshman-advising/resources.cfm
Dagemawit Kebede | SSSS | Carey Miller | Completed Edit |  | Information Library > Academic Support and Resources > Academic Support > Undergraduate Support > First-Time Undergraduate Advising > Your Classes Explained | ubalt.edu/academics/academic-support/freshman-advising/your-classes-explained.cfm | /myubalt/Information-Library/Academic-Support-and-Resources/Academic-Support/Undergraduate-Support/First-Time-Undergraduate-Advising/Your-Classes-Explained.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/academics/academic-support/freshman-advising/your-classes-explained.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/ub%20student%20emergency%20grant%20fund.cfm | /About/Offices-and-Services/Dean-of-Students/ub-student-emergency-grant-fund.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/ub%20student%20emergency%20grant%20fund.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/ubalt-connects | /About/Offices-and-Services/Dean-of-Students/dean-of-students/ubalt-connects.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/ubalt-connects
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/ubalt-connects/become-a-mentee.cfm | /About/Offices-and-Services/Dean-of-Students/ubalt-connects/become-a-mentee.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/ubalt-connects/become-a-mentee.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/ubalt-connects/index.cfm | /About/Offices-and-Services/Dean-of-Students/ubalt-connects/index.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/ubalt-connects/index.cfm
Dagemawit Kebede | SSSS | Anthony Butler | Completed Edit |  | Information Library > Campus Engagement > Student Engagement |  | /myubalt/Information-Library/Campus-Engagement/Student-Engagement.cfm | Intranet | Create Empty Page | Create | UBalt Outline
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | About > Offices & Services > Dean of Students > > > | ubalt.edu/about-ub/offices-and-services/dean-of-students/ubalt-connects/learn-more%20.cfm | /About/Offices-and-Services/Dean-of-Students/ubalt-connects/learn-more-.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/about-ub/offices-and-services/dean-of-students/ubalt-connects/learn-more%20.cfm
Dagemawit Kebede | SSSS | This page does not belong to SSSS. | Completed Edit |  | Information Library > Services > Space Reservations and Conference Services > Student Center > Interfaith Room Request | ubalt.edu/campus-life/student_center/interfaith-room-request.cfm | /myubalt/Information-Library/Services/Space-Reservations-and-Conference-Services/Student-Center/Interfaith-Room-Request.cfm | Intranet | Migrate | Keep (Revise) | Migration-Ready | This should belong to Auxiliary Services. EW: Migrate to form tool | ubalt.edu/campus-life/student_center/interfaith-room-request.cfm
Dagemawit Kebede | SSSS | This page does not belong to SSSS. | Completed Edit |  | Information Library > Services > Space Reservations and Conference Services > Student Center > Signage Request | ubalt.edu/campus-life/student_center/signage-request-form.cfm | /myubalt/Information-Library/Services/Space-Reservations-and-Conference-Services/Student-Center/Signage-Request.cfm | Intranet | Migrate | Keep (Revise) | Migration-Ready | This should belong to Auxiliary Services. EW: Migrate to form tool | ubalt.edu/campus-life/student_center/signage-request-form.cfm
Dagemawit Kebede | SSSS | Tony DuLaney | Completed Edit |  | Information Library > Services > Basic Needs | ubalt.edu/basic-needs | /myubalt/Information-Library/Services/Basic-Needs.cfm | Intranet | Migrate | Keep (As Is) | Migration-Ready | Reviewed by KM | ubalt.edu/basic-needs | Several links to external resources outside of the OSS purview are linking to dead sites - will need updated links.
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | Footer > Complaint Process | ubalt.edu/student-concerns.cfm | /Footer/Complaint-Process.cfm |  | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/student-concerns.cfm
Dagemawit Kebede | SSSS | Tony DuLaney - DELETE THIS PAGE | Completed Edit |  | Student Life > Student Support > Main > > > |  | /Student-Life/Student-Support/index.cfm | Interior | Create Empty Page | Create | iFactory Outline | This page already exisits and a new page does not need to be created ( we have placed a ticket to document this)
Dagemawit Kebede | SSSS | Stephen Mogar | Completed Edit |  | Student Life > Campus Resources > Student Handbook > > > | ubalt.edu/campus-life/student-handbook.cfm | /Student-Life/Campus-Resources/Student-Handbook.cfm | Interior | Migrate | Keep (As Is) | Migration-Ready |  | ubalt.edu/campus-life/student-handbook.cfm
Note on D73: María Maclay: Need to go over final language with Karyn.
Note on D81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I do not see this page.